## PO NOV Response to ODEQ
Item No. | Alleged Violation | CCC Comments | Compliance Plan/Corrective Actions | Status | Owner(s) | Measures Taken to Prevent Recurrence
1 (FCE Issue 1, NOV Issue 1) | Emissions Inventory not appropriately represented in 2022, 2023, and 2024 | CCC is actively working with Spirit Environmental to revise the Emissions Inventory to include this emergency generator for the reporting years of 2022, 2023, and 2024. The was merely an oversight on the part of CCC. | The CoGEN 1 Emission Inventories for 2022, 2023, and 2024 will be submitted by July 31, 2026. | In-progress | Spirit Env/ODEQ/Corp EHS | In the future, CCC will review final data used for Emission Inventory reporting purposes to ensure accuracy.
2 (FCE Issue 2, NOV Issue 2) | Operating emergency diesel generator Cogen 1 prior to submitting a minor modification application. | CoGEN 1 diesel generator was included in the August 8, 2025 PSD draft permit but was removed by ODEQ in the final version issued on August 18, 2025. | We formally request that ODEQ re-issue the permit directly that includesthe CoGEN 1 diesel emergency generator. | In-progress | Spirit Env/ODEQ/Corp EHS | We formally request that ODEQ re-issue the permit directly that includes the CoGEN 1 diesel emergency generator.
3 (FCE Issue 3, NOV Issue ) | LDAR inspections conducted late in 2023 and 2025 | LDAR inspections were conducted in 2023 and 2025 but not within a rolling 12-month period. | Re-training was conducted on June 22, 2026 with plant personnel who conducts LDAR inspections. | Completed | Corp EHS/Ponca EHS | Personnel training on the importance of conducting the inspections within the 12-month period will prevent recurrence.
4 (FCE Issue 4, NOV Issue 4) | Records of first attempt and final repair for LDAR components incomplete for 2023. | First attempt to repair was not documented; however, the second attempt and completion date of repair was documented. | Re-training was conducted on June 22, 2026 with plant personnel who conducts LDAR inspections. | Completed | Corp EHS/Ponca EHS | In the future, all documentation of first attempt and final repair will be maintained and provided upon request.
5 (FCE Issue 5, NOV Issue 5) | Failed to include a statement that "No leaks were detected or that inspections occurred" in the semi-annual MACT report. | The was merely an oversight on the part of CCC. | Re-training was conducted on June 26, 2026 with plant personnel who conducts LDAR inspections and assists with MACT reports. | Completed | Corp EHS/Ponca EHS | CCC will include the statement regarding findings of the LDAR inspection in each semi-annual MACT report going forward.
6 (FCE Issue 6, NOV Issue 6) | Failure to include all required information in the MACT periodic reports. | CCC will include the statement regarding findings of the LDAR inspection in each semi-annual MACT report going forward. | Re-training was conducted on June 26, 2026 with plant personnel who conducts LDAR inspections and assists with MACT reports. | Completed | Corp EHS/Ponca EHS | CCC will include all required information in the MACT periodic reports going forward.
7 (FCE Issue 7, NOV Issue 7) | Failed to include deviation table in SAR for period covering 8/1/2024-01/31/2025 | CCC will ensure that the deviation table is included with every SAR submittal going forward. | This requirement will be completed by Corp EHS from now on, instead of plant EHS personnel. The deviation table for the period covering 8/1/2024-01/31/2025 was mailed to ODEQ on August 28, 2025 via USPS Certified Mail. | Completed | Corp EHS | CCC will ensure that the deviation table is included with every SAR submittal going forward.
8 (FCE Issue 8, NOV Issue 8) | Compliance certification was not completed with all Specific Conditions in the PSD and TV permits for the period covering 08/1/2024 through 01/31/2025. | CCC will ensure that the ACC is certifying compliance with all conditions of actively issued permits going forward. | This requirement will be completed by Corp EHS from now on, instead of plant EHS personnel. Corrected compliance certifications will be submitted by July 31, 2026. | Completed | Corp EHS | CCC will ensure in the ACC to certify compliance with all conditions of actively issued permits going forward.
9 (FCE Issue 9, NOV Issue 10) | Deviations listed in the SARs (no dates associated with the alleged sumittals), include emission events (EEs) which list "Carbon Black" as the pollutant when it should be classified as PM. | CCC will ensure that the correct pollutant is reported in EEs going forward. | Compliance achieved July 9, 2026. | Completed | Corp EHS | CCC will ensure that the correct pollutant is reported in EEs going forward.
10 (FCE Issue 10, NOV Issue 10) | Deviations listed in the SARs (no dates associated with the alleged sumittals), did not include non-EE violations of current permits. | CCC will ensure that the deviation table includes description of permit-relation violations, in addition to any EEs that might have happened in the SAR reporting period. | CCC has updated its form deviation table to include all violations, including EEs. Compliance achieved July 9, 2026. | Completed | Corp EHS | The new form will ensure compliance going forward.
11 (FCE Issue 11, NOV Issue 8) | Emission point listed in the EE report does not always match permit emission point. | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | Additional training and internal procedures will ensure excess emission reports are accurate going forward.
12 (FCE Issue 12, NOV Issue 9) | Immediate EE notice for event HQB-0P39-5WVXA that occurred on 12/23/2024 was not reported. | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | CCC has created a procedure to help reduce the late and insufficient EE reports.
13 (FCE Issue 13, NOV Issue 7) | 30-day EE report was submited 19 days late for HQB-0P39-5WVXA. | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | Additional training and internal procedures will ensure excess emission reports are accurate going forward.
14 (FCE Issue 14, NOV Issue 7) | 30-day EE report was submited 1 day late for HQG-2NX0-RSYY6. | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | Additional training and internal procedures will ensure excess emission reports are accurate going forward.
15 FCE Issue 15, NOV Issue 10) | Wrong event date was listed on EE report HQG-2NX0-RSYY6. | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | Additional training and internal procedures will ensure excess emission reports are accurate going forward.
16 FCE Issue 16, NOV Issue 11) | Incorrect emission limit was listed in EE report HQD-91MW-W7314. | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | Additional training and internal procedures will ensure excess emission reports are accurate going forward.
17 FCE Issue 17, NOV Issue 11) | Incorrect emission limit was listed in EE report HQG-C42E-266FT. | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | Additional training and internal procedures will ensure excess emission reports are accurate going forward.
18 FCE Issue 18, NOV Issue 11) | Incorrect emission limit was listed in EE report HQG-DNST-CP3V5. | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | Additional training and internal procedures will ensure excess emission reports are accurate going forward.
19 FCE Issue 19, NOV Issue 11) | Incorrect emission limit was listed in EE reports HQM-NM55-4MP29 and HQP-6YRM-TCP5B. | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | Additional training and internal procedures will ensure excess emission reports are accurate going forward.
20 FCE Issue 20, NOV Issue 11) | Incorrect emission limit was listed in EE report HQP-6YGV-NB92M. | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | Additional training and internal procedures will ensure excess emission reports are accurate going forward.
21 FCE Issue 21, NOV Issue 11) | Incorrect emission limit was listed in EE report HQP-1Q3P-AX916. | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | Additional training and internal procedures will ensure excess emission reports are accurate going forward.
22 FCE Issue 22, NOV Issue 12 | Failure to accurately report primary cause on four EE reports (either malfunction, shutdown or startup). | CCC has created a procedure to help reduce the late and insufficient EE reports. | Re-training on reporting excess emission reporting will was conducted with Plant EHS employees on July 7, 2026 . CCC has created an internal procedure to help reduce the late and insufficient EE reports. | Completed | Corp EHS/Ponca EHS | Additional training and internal procedures will ensure excess emission reports are accurate going forward.
23 FCE Issue 23, NOV Issue 14 | Nine EE events exceeded the allowable limits for lb/hr PM from Unit 1/EPN#3 | CCC Ponca City Plant conducted major MBF repairs to Unit 1 in 2025. These repairs have greatly reduced the PM excursions from Unit 1. CCC made the appropriate notifications to ODEQ. | CCC Ponca City Plant conducted major MBF repairs to Unit 1 in 2025. These repairs have greatly reduced the PM excursions from Unit 1. | Completed | Plant Operations | Continous monitoring and operator training will ensure excess emissions from Unit 1/EPN #3 will not occur going forward.
24 FCE Issue 24, NOV Issue 14 | EE event exceeded the allowable lb/hr PM for Unit 2/EPN#7. | Unit 2 MBFs developed leaks, which caused the event. CCC made the appropriate notification to ODEQ. CCC made the appropriate notification to ODEQ. | Maintenance and bag replacements on Unit 2 MBFs was conducted, which prevented a reccurrence. | Completed | Plant Operations/Plant EHS/Corp EHS | CCC Ponca City conducts routine maintenance on all MBFs to ensure excess emissions do not occur.
25 FCE Issue 25, NOV Issue 14 | EE event exceeded the allowable lb/hr PM for Unit 3/EPN#11. | Reactor 31 air preheater developed a leak. The unit oiled in at 5:13 AM, upon discovery of the leak, the facility immediately oiled out 7:17 AM to stop the excess emissions. CCC made the appropriate notification to ODEQ. | CCC Ponca City maintenance removed the old expansion joint and replaced it with new expansion joints. This resolved the equipment malfunction on the air preheater and is operating without any incidents. | Completed | Plant Operations/Plant EHS/Corp EHS | CCC Ponca City conducts continous monitoring and operator training to reduce incidents recurring. Additionally, routine maintenance on all reactors are conducted to ensure excess emissions do not occur.
26 FCE Issue 26, NOV Issue 14 | Six EE events exceeded the allowable lb/hr PM for CGEU 1/EPN#40. | The high NOx emissions were due to the ammonia gun being chocked. CCC made the appropriate notifications to ODEQ. | The ammonia gun was cleaned and has been operating without any incidents. | Completed | Plant Operations/Plant EHS/Corp EHS | All CCC Ponca City operators go through extensive training in order to reduce incidents.
27 FCE Issue 27, NOV Issue 14 | Event HQD-G6V8-6N05V exceeded 7 days - possible mitigation due to malfunction as cause of event and exceedance of PM for CGEU 1/EPN#40 | Stack 1 developed a leak in compartment C. Once the unit was safe for entry, it was discovered that 3 bags needed replacing. CCC made the appropriate notification to ODEQ. | Maintenance was conducted and all leaking bags were replaced. | Completed | Plant Operations/Plant EHS/Corp EHS | All CCC Ponca City operators go through extensive training in order to reduce incidents.
28 FCE Issue 28, NOV Issue 14 | Two EE events lasted less than 7 days and exceeded the 7-day rolling average for SO2 limits for CGEU1/EPN#40. | The exceedance of SO2 was due to a recalibration issue of the CEMS unit and lime that had solidified on trough hopper #1. When the lime solidifies, air flow becomes restricted, and SO2 emissions increase. CCC made the appropriate notifications to ODEQ. | The CEMS unit was recalibrated and corrected. The hopper was cleaned and the solidified lime was removed to establish normal process flow. | Completed | Plant Operations/Plant EHS/Corp EHS | All CCC Ponca City operators go through extensive training in order to reduce incidents.
29 FCE Issue 29, NOV Issue 14 | Three EE events lasted 7 days or more and exceeded the 7-day rolling average for SO2 limits for CGEU1/EPN#40. | The SO2 exceedence was due to a bag blocking the recirculation valve, which prevents sufficient air flow to reduce the SO2 emissions. CCC made the appropriate notification to ODEQ. | CCC Ponca City stopped activities which allowed for the unit to be cleaned and remove the blocked bag. | Completed | Plant Operations/Plant EHS/Corp EHS | All CCC Ponca City operators go through extensive training in order to reduce incidents.
30 FCE Issue 30, NOV Issue 13 | Six opacity events exceeded 20% opacity from Production Unit 1/EPN#3. | The events occurred on different days and were due to different reasons. Unit 1 MBF starting leaking due to a hole in the roof. The air preheater for reactor 12 expansion joint developed a leak. The MBFs and EBFs on Unit 1 all burned down. Each incident was prompty addrssed and was reported to ODEQ. CCC made the appropriate notifications to ODEQ. | Once safe for entry, the compartment was isolated and repairs were successfully completed on Unit 1 MBF. Reactor 12 air preheater was isolated and an expansion joint wrap was applied and repairs were successfully made. Replacement of all bags on all compartments for Unit 1 MBFs and EBFs were successfully made. Extensive repairs were conducted on Unit 1 in 2025, which has greatly reduced events from recurring. | Completed | Plant Operations/Plant EHS/Corp EHS | CCC Ponca City conducts continous monitoring and operator training to reduce incidents recurring. Additionally, routine maintenance on all reactors and baghouses are conducted to ensure excess emissions do not occur.
31 FCE Issue 31, NOV Issue 13 | An opacity event exceeded 20% opacity from Unit 2/EPN #7. | MBFs for Unit 2 developed a leak. Upon discovery of the opacity event, the unit ceased operations until the source of the issue could be identified. CCC made the appropriate notification to ODEQ. | Once safe for entry, the leaks were identified and bag repairs were successfully completed. | Completed | Plant Operations/Plant EHS/Corp EHS | CCC Ponca City conducts continous monitoring and operator training to reduce incidents recurring. Additionally, routine maintenance on all reactors and baghouses are conducted to ensure excess emissions do not occur.
32 FCE Issue 32, NOV Issue 13 | Six opacity events exceeded 20% opacity from CGEU 1/EPN#40. | The events occurred on different days and were due to different reasons. Unit 2 developed a leak in the exhaust, which was repaired. Unit 1 EBF developed a leak, which was repaired. Unit 3 MBF developed a leak, which was repaired. CCC made the appropriate notifications to ODEQ. | Unit 2 EBF repairs were successfully completed, which reduced the occurrence of events. All compartments in Unit 2 EBF underwent a complete a bag replacement. Unit 3 compartments were isolated so that repairs could be successfully completed. | Completed | Plant Operations/Plant EHS/Corp EHS | CCC Ponca City conducts continous monitoring and operator training to reduce incidents recurring. Additionally, routine maintenance on all reactors and baghouses are conducted to ensure excess emissions do not occur.
33 FCE Issue 33, NOV Issue 13 | Event HQD-G6V8-6N05V exceeded 7 days - possible mitigation due to malfunction as cause of event and exceeded 20% opacity at CGEU 1/EPN#40 | Compartment C to stack 1 was isolated and operations ceased until repairs could be made. CCC made the appropriate notification to ODEQ. | Leaking bags were successfully replaced in all compartments, which has prevented the recurrence of this event. | Completed | Plant Operations/Plant EHS/Corp EHS | CCC Ponca City conducts continous monitoring and operator training to reduce incidents recurring. Additionally, routine maintenance on all reactors and baghouses are conducted to ensure excess emissions do not occur.
34 | Exceedance of NOx, PM, CO, VOC, and SO2 in 2022, 2023, 2024, and 2025. | CCC was issued Consent Order 25-026 for exceeding CO and PM in 2022 and 2023. NOV No. 26-AQN-002 mentions a draft TV permit; however, ODEQ has not provided CCC with this draft permit. CCC was issued Consent Order 25-026 for exceeding CO and PM in 2022 and 2023. CCC mailed the penalty payment to ODEQ via certified mail on June 29, 2026. This violation should not include the emission exceedances that have already been addressed. When ODEQ was evaluating EIs for 2022, 2023, and 2024, why didn't they address the NOx, CO, VOC and SO2 exceedances? | EHS to review emissions on a monthly basis with Plant Management. | In-progress | Corp EHS | EHS Emissions Review with leadership on a monthly basis will keep the plant aware of our limits so they can adjust operations, if needed.
35 FCE Issue 35, NOV Issue 16 | Failure to provide records of transition events in SAR submittals. | CCC will ensure that all required documentation is submitted with SARs going forward. This documentation was provided to ODEQ during their initial request. | This requirement will be completed by Corp EHS from now on, instead of plant EHS personnel. | Completed | Corp EHS | The transfer of responsibility for ensuring SAR submittals are complete will ensure compliance going forward.
36 FCE Issue 36, NOV Issue 16 | Failure to provide records of transition events in SAR submittals. | CCC provided ODEQ a complete list of all transition events from August 2024-January 2026. This list is a complete record, showing the total number of transition events in a 12-month period. | CCC has trained staff on the requirement to maintain 12-month rolling totals for transition events. | Completed | Plant Operations/Plant EHS/Corp EHS | The transfer of responsibility for ensuring SAR submittals are complete will ensure compliance going forward.
37 FCE Issue 37, NOV Issue 17 | Exceeded the 10- minute transition limit 154 times between Jan 2024 and Jan 2026. | CCC Ponca City had failing waste gas control valves on both boilers. The replacements for these valves have a 36-week lead time. The plant was able to stay operational by manually operating the sticking valves. This caused longer times to establish waste gas into the boilers, not allowing the vent stacks to be closed in the ten-minute window. While the plant stayed operational, the valve replacements had to take place one boiler at a time. Starting with the System 2 boiler, the valves had to be removed and were then sent to the machine shop for rebuild. When the refurbished valves were completed, they were successfully installed on System 2 boiler. System 1 boiler was then maintenanced by the same process as System 2 boiler. We do have two spare valves on standby. Proper notifications wwere submitted to ODEQ for each of these events. | CCC has had spare valves built to limit the transition event times. | Completed | Plant Operations/Plant EHS/Corp EHS | CCC Ponca City conducts continous monitoring and operator training to reduce incidents recurring. Additionally, routine maintenance on all boiler systems are conducted to ensure the transition time is not exceeded.
38 FCE Issue 38, NOV Issue 18 | 7-Day Rolling and 365-Day Rolling for SO2 and NOx, request included Jan 2026 but did not receive. | Jan 2026 records were inadvertently not included in the submission to DEQ. January 2026 7-Day Rolling and 365-Day Rolling for NOx and SO2 are provided with this response. | Ponca City has all CEMS data readily available for review at request of ODEQ. | Completed | Corp EHS | NA
39 FCE Issue 39, NOV Issue 43 | Failed to provide SO2 and NOx CEMS data in last 3 SARs. | CCC will ensure that all required documentation is submitted with SARs going forward. This documentation was provided to ODEQ during their initial request. | This documentation was provided to ODEQ on April 30, 2026. This requirement will be completed by Corp EHS from now on, instead of plant EHS personnel. | Completed | Corp EHS | CCC will ensure that all required documentation is submitted with SARs going forward.
40 FCE Issue 40, NOV Issue 18 | SO2 exceedances from August 2024 - January 2026 for CGEU1 (total of 45 days) | Extensive repairs were made to CGEU1 in 2025, which has greatly reduced the exceedances of SO2. Proper notifications were submitted to ODEQ for each of these events. | Repairs conducted to CGEU1 will prevent recurrence of the exceedances. | Completed | Plant Operations/Plant EHS/Corp EHS | CCC Ponca City conducts continous monitoring and operator training to reduce incidents recurring. Additionally, routine maintenance on all CGEUs are conducted to ensure the transition time is not exceeded.
41 FCE Issue 41, NOV Issue 18 | SO2 exceedances from August 2024 - January 2026 for CGEU2 (total of 31 days) | Extensive repairs were made to CGEU2 in 2025, which has greatly reduced the exceedances of SO2. Proper notifications were submitted to ODEQ for each of these events. | Repairs conducted to CGEU2 will prevent recurrence of the exceedances. | Completed | Plant Operations/Plant EHS/Corp EHS | CCC Ponca City conducts continous monitoring and operator training to reduce incidents recurring. Additionally, routine maintenance on all CGEUs are conducted to ensure the transition time is not exceeded.
42 FCE Issue 42, NOV Issue 18 | NOx exceedances from August 2024 - January 2026 for CGEU2 (total of 17 days) | Extensive repairs were made to CGEU2 in 2025, which has greatly reduced the exceedances of SO2. Proper notifications were submitted to ODEQ for each of these events. | Repairs conducted to CGEU2 will prevent recurrence of the exceedances. | Completed | Plant Operations/Plant EHS/Corp EHS | CCC Ponca City conducts continous monitoring and operator training to reduce incidents recurring. Additionally, routine maintenance on all CGEUs are conducted to ensure the transition time is not exceeded.
43 FCE Issue 43, NOV Issue 18 | Failed stack test for PM for CGEU1 and CGEU2, last tested in Oct 2022. This concludes that COGENs have been operating out of compliance with PM limits. | The was merely an oversight on the part of CCC. | CCC has scheduled a stack test to be performed on CGEU1 and CGEU2 on July 21st and July 22nd. Notification was made to ODEQ on June 8, 2026. Additionally, this requirement has been added to our internal EHS tracking system. | In-progress | Corp EHS/Plant Operations/Air Hygiene | Training for EHS staff and Plant Management will prevent recurrence.
44 FCE Issue 44, NOV Issue 18 | NOx cap for Heat Load was exceeded for the period of August 2024 through January 2026 and not provided in 365-day rolling average. | CCC considers "Heat Load" as startup and shutdown; therefore, "Heat Load" emissions captures both startup and shutdown. The timeframe of August 2024 through January 2026 for NOx exceedances was due to an increase in equipment malfunctions, which caused an unusual amount of startup and shutdown events. | Major reactor repairs to all units have been completed. CCC provided the NOx emissions for Heat Load to ODEQ during initial request, on April 30, 2026. The 365-Day Rolling Average is included with this submittal. | Completed | Corp EHS/Plant Operations | Major equipment repairs that were made will prevent recurrence. Additionally, a monthly review of NOx cap emissions will be scheduled between Corp EHS and Plant Management to ensure the 50 TPY cap is not exceeded.
45 FCE Issue 45, NOV Issue 19 | CO and NOx exceedances in 2022, 2023, and 2024. Newly issued permit increased emission limits, no further action. | Consent Order 25-026 was executed on May 11, 2026 addressing the CO excedences in 2022 and 2023. This violation should not include the CO exceedances that CCC has already been sited for. | CCC requested permit increase; ODEQ issued permit in August 2025. | Completed | Corp EHS | NA
46 FCE Issue 46, NOV Issue 20 | SO2 scrubber removal efficiency is at 93.56%, which is below the required 95% removal efficiency. | CCC's DCS Control Philosophy produces a removal efficiency of 96.02% SO2. The supporting documentation is provided with this response. | In CCC's initial response to ODEQ, the equation provided was for maximum operation, which is not a protocol that the Ponca City plant uses. The original equation provided by the manufacturer was modified and improved to increase the efficiency of the SO2 removal, which provides a >95% removal efficiency, which is built on the DCS. See attachment provided with this response. | Completed | Corp EHS | NA CCC Ponca City operates the DCS with a SO2 removal efficiency of 96.02%.
47 FCE Issue 47, NOV Issue 21 | Cylinder gas audits were not conducted quarterly from Jan 2024 - Dec 2025. | CCC has trained CoGEN and plant EHS on quarterly gas audits. | Q2 2026 CGA was conducted successfully on May 12th and 13th. | Completed | Corp EHS/Plant Operations/Plant EHS | Training for EHS staff will prevent recurrence.
48 | Intermittent CEMS readings during the last 2 quarters of 2024 indicates that the COGEN U1 was operational. Additionally, CEMS downtime report was not included in the CD Progress Reports. | CCC has provided the instances where waste gas is either entering the furnace or not. There was a time period during the last half of 2024 where turbine 1 was offline for an extended period, but the plant can still pipe the steam from boiler 1 to turbine 2. All CEMS downtime has been provided in this response. | CCC will include all CEMS downtime in the CD Progress reports going forward. | Completed | Corp EHS/Plant Operations/Plant EHS | Training for EHS staff will prevent recurrence.
49 | 2023 RATA failed test for NOx. Also, the summary page did not include units listed in ppmvw @ 0% O2. | The 2023 RATA for CGEU2 passed for all parameters. The initial RATA summary page provided from Air Hygiene did not include the units in ppmvw @0%. This has been rectified and the 2023 RATA summary is provided in this response. | CCC performed a succssful RATA in December 2023. | Completed | Plant EHS/Corp EHS/Plant Operations/Air Hygiene | CCC will ensure that all required documentation is submitted with SARs going forward.
50 | Failed to conduct RATA in 2024. | CCC submitted reschedule notifications to ODEQ, explaining that CGEU1 was not operational. The first reason was due to a catostrophic equipment failure; therefore, a RATA could not be performed. Shortly after, inclement weather prohibited a RATA from being performed, which CCC made notification to ODEQ. All were beyond the control of CCC and proper notifications were made to ODEQ. Additionally, this information was included in the CD Progress Report #20. | CCC performed a successful RATA in Feb 2025. | Completed | Plant EHS/Corp EHS/Plant Operations | NA
51 | Failed to conduct a RATA in a timely manner. | The previous RATA was conducted in Feb 2025, making the next RATA due in the first quarter of 2026. The RATA was performed within four calendar quarters. | CCC performed a successful RATA in January 2026. | Completed | Plant EHS/Corp EHS/Plant Operations | NA
52 | RATA results from 2024 and 2025 were not submitted to ODEQ within 60 days of completion | CCC uses Air Hygiene to perform the RATAs and thought they were submitting the test results to ODEQ within the required 60 days. | CCC will submit all RATA tests results directly to ODEQ going forward. | Completed | Corp EHS/Plant EHS | Training for EHS staff will prevent recurrence.
53 | Stack test for PM was not conducted in 2023, 2024, and 2025. | This was merely an oversight on the part of CCC. | CCC has scheduled a stack test to be performed on CGEU1 and CGEU2 on July 21st and July 22nd. Notification was made to ODEQ on June 8, 2026. | Completed | Plant EHS/Corp EHS/Plant Operations | Training for EHS staff will prevent recurrence.
54 FCE Issue 54, NOV Issue 24 | Exceeded NOx and PM emission limits in all six dryers in 2025; exceeded VOC emission limits from 2022 - 2025 from dryer 41. | The timeframe of 2022 - 2025 for NOx and PM exceedances was due to an increase in equipment malfunctions, which caused an unusual amount of startup and shutdown events. | Major repairs associated to all reactor units have been completed. These repairs have greatly reduced the emissions from the Dryers. | Completed | Plant EHS/Corp EHS/Plant Operations | CCC Ponca City conducts continous monitoring and operator training to reduce incidents recurring. Additionally, routine maintenance on all reactors and associated equipment is conducted to ensure emissions are not exceeded.
55 FCE Issue 55, NOV Issue 26 | Failure to meet 99% collection efficiency of PM from carbon black tanks. Current dust collectors efficiency is 85-90%. This requirement is per CD, Appendix A and Appendix D. | The Donaldson Torit Power Core Ultra-Web filer series captures 95%-99% of PM particles, per the National Air Filtration Association. The specification sheet is included with this response. | CCC is compliant with the PM collection efficiency for the carbon black tanks. | Completed | Plant EHS/Corp EHS/Plant Operations | NA
56 FCE Issue 56, NOV Issue 27 | Failure to demonstrate compliance with Baghouse Recordkeeping Plans. | Permit No. 2017-0914-C (M-3) SC 9(d) only requires CCC to "keep and maintain" a Baghouse Recordkeeping Plan. Submitting this Plan as part of our SARs is not applicable to Standard Condition III C. Since all the Main Bag Filter (MBFs) Baghouses use the same plan, the Plant only maintains a single plan for all. They are all designed and operationally the same; there is not a need for individual MBF Plans for each unit. | CCC provided ODEQ a complete record of all baghouse type and maintenance dates at the initial and second request. All bags are authorized for disposal at American Environmental Landfill, and CCC maintains copies of all manifests for review. | Completed | Corp EHS/Plant EHS | NA
57 FCE Issue 57, NOV Issue 27 | Failure to demonstrate compliance with Baghouse Recordkeeping Plans. | CCC keeps and maintains all waste manifests for disposal of used bag filters. CCC | CCC inadvertently left out the disposal records and has provided them with this response. All bags are authorized for disposal at American Environmental Landfill; copies of all manifests are provided with this response. | Completed | Corp EHS/Plant EHS | NA - CCC has been keeping and maintaining the records as required by the Permit.
58 | Failure to maintain records of spills and leaks of CB. | CCC utilizes two industrial powered sweepers throughout the plant on a daily basis. | Re-training on proper documentation of all leaks and spills was conducted on June 24, 2026 with EHS Plant personnel. Copies of spills and leaks documentation is included with this response. | Completed | Corp EHS/Plant EHS | This task has been added to the EHS compliance tracker.
59 | Failure to conduct Method 22 assessments on all equipment; shipping failed to conduct Method 22 assessments on weekends and holidays. | CCC was not asked to expand on the data that was provided to ODEQ regarding the Method 22 locations. However, CCC is more than happy to share with ODEQ what equipment correlates to Locations 1, 2, 3, 4 and 5. Each location reviews different areas of the plant. By conducting assessments on Locations 1, 2, 3, 4 and 5, all equipment has a Method 22 assessment completed. The Shipping department does not operate on the weekends or holidays; hence, there is not a requirement to conduct a Method 22 assessment in the Shipping Locations during non-operating days. CCC does conduct daily Method 22 assessments consistently on all required equipment; therefore, these records are complete. | CCC documents the Method 22 assessments with a "Completed" which indicates that no visible emissions were discovered. In the event that visible emissions are observed, a notation of "VE" will be recorded. A Location Summary is attached with this response. | Completed | Plant EHS/Corp EHS/Plant Operations | NA CCC conducts Method 22 on all equipment.
60 FCE Issue 60, NOV Issue 29 | Failed to record all Method 22 assessments. Failure to include Method 22 records in SAR submittals. | CCC does maintain Method 22 records and are readily available for review at the request of ODEQ. CCC provided these records to ODEQ during their initial request for records, on April 30, 2026. | CCC documents the Method 22 assessments with a "Completed" which indicates that no visible emissions were discovered. In the event that visible emissions are observed, a notation of "VE" will be recorded. A Location Summary is attached with this response.CCC will include all Method 22 assessments in SARs going forward. | Completed | Corp EHS/Plant EHS | NA CCC conducts Method 22 on all equipment.
61 FCE Issue 61, NOV Issue 30 | Failure to conduct Method 9 assessments due to unconfirmed Method 22 assessments. | This is a repeat violation of NOV #60. CCC was not provided the opportunity to describe the recordkeeping of our Method 22 assessments. This does not automatically qualify for non-compliance with the visible emission regulations. CCC provided ODEQ all Method 9 readings at the inital request. If ODEQ could not confirm compliance, why was CCC not afforded the opportunity to clarify? | CCC documents the Method 22 assessments with a "Completed" which indicates that no visible emissions were discovered. In the event that visible emissions are observed, a notation of "VE" will be recorded. A Location Summary is attached with this response.CCC will include all Method 22 assessments in SARs going forward. | Completed | Plant EHS/Corp EHS/Plant Operations | NA CCC conducts Method 22 on all equipment.
62 FCE Issue 62, NOV Issue 31 | Failure to include all emergency generator maintenance records in SARs. | CCC does annuall maintenance on emergency generators and will include this information in SARs going forward. | CCC will include all mainteance records for emergency generators in SARs going forward. | Completed | Corp EHS/Plant EHS | CCC does annaul mainteance on emergency generators and will include this information in SARs going forward.
63 FCE Issue 63, NOV Issue 31 | Failure to conduct maintenance on emergency generators within a 12-month period. | CCC will ensure that all requirements of Subpart ZZZZ are met going forward. Maintenance is conducted quarterly on each emergency generator. | On July 6, 2026, CCC has communicated with the contractor who services our emergency generators regarding this requirement. Re-training of this requirement with plant personnel was conducted on July 2, 2026. | Completed | Corp EHS/Plant EHS | Training for staff and contractor will prevent recurrence. CCC will ensure that all requirements of Subpart ZZZZ are met going forward.
64 FCE Issue 64, NOV Issue 31 | Failure to include emergency generator hours in Feb 2025 SAR and Feb 2026 SAR. | CCC will ensure that all required documentation is submitted with SARs going forward. This documentation was provided to ODEQ on April 30, 2026. | This requirement will be completed by Corp EHS from now on, instead of plant EHS personnel. | Completed | Corp EHS | CCC will ensure that all required documentation is submitted with SARs going forward.
65 FCE Issue 65, NOV Issue 32 | Emergency Generator Unit 2 ran for 168 hours in 2023, which exceeded the 100-hr annual limit for maintenance and readiness testing. | CCC does not have an Emergency Generator Unit 2; however, Ponca has a Unit named Unit 1&2 which ran for a total of 63.2 hours in 2023. The Generator Hours Tracking Spreadsheet is included with this response. | CCC is compliant with the operating hour limitations for emergency generators. | Completed | Corp EHS/Plant EHS | NA
66 FCE Issue 66, NOV Issue 33 | Failure to provide a biennial report for the period January 1, 2024 to December 31, 2025 by January 31, 2026. | CCC re-trained staff on Date on the importance of ensuring required reports are submitted timely. The boiler MACT report was submitted to ODEQ on May 21, 2026. | Boiler MACT report was submitted to ODEQ on May 21, 2026. | Completed | Corp EHS/Plant EHS | CCC will ensure that required reports are submitted timely going forward.
67 FCE Issue 67, NOV Issue 36 | Failure to accurately report boiler tune date up in notifcation report. | CCC re-trained staff on Date on the importance of ensuring required reports are submitted timely. The boiler MACT report was submitted to ODEQ on May 21, 2026. | Boiler MACT report was submitted to ODEQ on May 21, 2026. | Completed | Corp EHS/Plant EHS | CCC will ensure that tune-up dates are accurately reported going forward.
68 FCE Issue 63, NOV Issue 35 | Failure to conduct tune-up and burner inspection. | ODEQ was unable to determine compliance with the records that CCC provided. However, CCC was not afforded the opportunity to discuss the activities conducted before ODEQ issued a violation for this requirement. A full and completed tune-up and inspection was performed in 2024 and 2026 and was submitted to ODEQ on April 30, 2026. | CCC provided the boiler inspections from 2024 and 2026 to ODEQ on April 30, 2026. | Completed | Corp EHS/Plant EHS | NA
69 FCE Issue 69, NOV Issue 47 | Failure to report all WEG (transition reports) in SARs. | CCC will ensure that all required documentation is submitted with SARs going forward. This documentation was provided to ODEQ during their initial request. | This requirement will be completed by Corp EHS from now on, instead of plant EHS personnel. | Completed | Corp EHS | CCC will ensure that all required documentation is submitted with SARs going forward.
70 FCE Issue 70, NOV Issue 48 | Failure to report accurate analyses of sulfur content of feedstock in SARs. | The Feedstock and Product report gives CCC a weekly composite sample of the sulfur percentage. The Sulfur report lists the daily sulfur percentages with the weekly average highlighted in yellow. It also breaks out the daily and weekly average composite samples by unit. The highlighted weekly average on the sulfur report matches the weekly sulfur percentage on the percentage Feedstock and Product report. ODEQ did not afford CCC the opportunity to explain the reports before issuing a violation for non-compliance. The Feedstock and Product Report and Sulfur Report accurately report sulfur content and were submitted to ODEQ on April 30, 2026. | CCC is compliant with the Sulfur reporting requirements. | Completed | Plant EHS/Plant Lab/Plant Operations | NA
71 FCE Issue 71, NOV Issue 49 | Failure to provide records of operation and maintenance for CGEUs. | Records of operation of the CGEUs are provided in the SAR and MACT YY report. The hours of operation of the CGEUs are listed as "Co-Gen Waste Gas Boiler 1" and Co-Gen Waste Gas Boiler 2"; the system cannot operate unless the boilers are operating, they are co-dependent. The maintenance of the CGEUs is partly done by Cemtek, as the CEMS is a part of the CGEU system. CCC is happy to provide additional maintenance records to demonstrate compliance with ODEQ's request, see the attached invoices for maintenance work with this response. | CCC is compliant with the requirements for CGEUs operation and maintenance. | Completed | Corp Accounts Payable/Corp EHS | NA
72 FCE Issue 72, NOV Issue 53 | Failure to provide ODEQ volume of natural gas usage. | CCC provided hours of natural gas usage, the provision of volume was an oversight. The information will be provided with this response. | CCC to provide ODEQ additional records of volume of natural gas used. | Completed | Plant Operations | CCC will ensure the required volume of natural gas is included going forward.
73 FCE Issue 73, NOV Issue 36 | Failure to request a modification to Permit No. 2017-0914-TVR2 within 180 days of issuance of the construction permit. | CCC requested the permit modification on May 2, 2026 to ODEQ. | CCC requested the permit modification on May 2, 2026 to ODEQ. | Completed | Corp EHS | CCC will ensure future permit modifications are requested timely.
74 FCE Issue 74, NOV Issue 37 | Failure to provide records of semi-annual and annual PM sensor inspections. | CCC inspects all PM sensors on a weekly basis. According to Permit No. 2017-0914-C (M-3), CCC is required to inspect the sensors on a semi-annual and annual basis. The current protocol is that every sensor is inspected and cleaned weekly, which is 50 times more than the current requirement. According to Permit No. 2017-0914-C (M-3), SC 24, "PM Sensors and PM Early Warning Systems are operated and maintained per manufacturer's recommendation". The manufacturer's recommendation regarding maintenance is found on page 34 of the Operating Manual which states that preventative maintenance should be checked "at regular intervals". CCC Ponca City facility is meeting this requirement. | CCC is compliant with the PM sensor inspection protocol requirement. CCC Ponca City provided these inspections to ODEQ on April 30, 2026. | Completed | Plant I&E | NA
75 FCE Issue 75, NOV Issue 50 | Failure to provide all "out-of-range"waste gas combustor temperatures in the January 2026 SAR. | CCC maintains records for "out-of-range" waste gas combustor temperatures and are available for review when requested by ODEQ. CCC will ensure that all required documentation is submitted with SARs going forward. This documentation was provided to ODEQ during their initial request, on April 30, 2026. | The SARs requirement will be completed by Corp EHS from now on, instead of plant EHS personnel. | Completed | Corp EHS | CCC will ensure that all required documentation is submitted with its SARs going forward.
76 FCE Issue 76, NOV Issue 38 | Failure to provide explanations during periods when the waste gas combustor temperatures were "out-of-range". | This is the first request that CCC has received from ODEQ to "include an explanation" for the waste gas combustor temperatures that were "out-of-range". The initial Records Request No. 23 included records for all waste gas combustors that fell outside the established temperature range. However, Records Request No. 23 did not ask for an explanation for these periods of time. CCC is providing the explanations for the waste gas combustor temperatures that were "out-of-range" in this NOV response. | CCC currently submits explanations for all "out-of-range" temperatures in SARs submittals. | Completed | Plant EHS/Corp EHS/Plant Operations | CCC will ensure that future SAR submittals include all required information.
77 FCE Issue 77, NOV Issue 38 | Failure to demonstrate compliance with the 1,500 degree limit for the waste gas combustors due to a lack of records. | This is a repeat of the above and should not be an additional violation. CCC provided all records for waste gas combustors that fell below the 1,500 degree limit for December 2025 and January 2026 as part of ODEQ's initial request, submitted on April 30, 2026. | CCC provided all records for waste gas combustors that fell below the 1,500 degree limit for December 2025 and January 2026 as part of ODEQ's initial request on April 30, 2026. | Completed | Plant EHS/Corp EHS/Plant Operations | NA
78 FCE Issue 78, NOV Issue 51 | Failure to conduct annual verification of the thermocouples on the waste gas combustors. | CCC submitted thermocouple calibrations in SARs to ODEQ; SAR 2/1/25 - 7/31/25 postmarked August 28, 2025 with USPS Certified Mail Receipt 7021272000034936613; SAR 2/1/24 - 7/31/24 - Mailed 8/20/24 Certified Mail Receipt - Tracking 9590 9402 8721 3310 4543 03; SAR 8/1/24 - 1/31/24 - Mailed 2/24/25 Certified Mail Receipt - Tracking 9590 9402 9166 4225 2181 85; SAR 8/1/25 - 1/31/26 - Sent DEQAQDComplianceEnfo@deq.ok.gov 2/26/26 - ID 2717 -944 and 2717908 Mailed 3/3/26 Tracking 9500 1139 7606 6062 9660 66. Additionally, a copy of the calibration records are included in this response. | CCC will continue to send the waste gas thermocouple requirements to ODEQ in SARs. | Completed | Plant I&E/Plant EHS | NA
79 FCE Issue 79, NOV Issue 61 | CD Progress Report Nos. 20 and 21 were submitted 1 day late. | CCC submitted these reports in good faith, as end of the month was in compliance the the CD Progress Reporting Requirements. | CCC will ensure the CD Progress Reports are post-marked by the 30th of January and July going forward. | Completed | Corp EHS | Additional training and internal procedures will ensure timely reporting going forward.
80 FCE Issue 80, NOV Issue 62 | Failure to provide all required documentation in the CD Progress Reports. Additionally, the PM Alarm Events do not include an explaination. | CCC has historically submitted these reports with the guidance of an attorney, who reviewed the report contents for accuracy. CCC believed that the reports were sufficient to meet the CD Progress Report requirements. However, CCC appreciates the opportunity to correct this oversight. PM Alarm Events are submitted with every CD Progress Report, with an explaination as to why the alarm was triggered in the "Remarks" column. | CCC will ensure that all the required documentation of Paragraph 53 are included in CD Progress Reports going forward. | Completed | Corp EHS | Additional training and internal procedures will ensure timely reporting going forward.
81 FCE Issue 81, NOV Issue 64 | Failure to provide the EPA and ODEQ with a 30-day notification for any violation of the CD. | CCC appreciates the opportunity to correct this oversight. | 30-day CD reports will be submitted to ODEQ and EPA going forward. CCC submitted a 30-day report on June 29, 2026 with the EPA and ODEQ. | Completed | Corp EHS | Additional training and internal procedures will ensure timely reporting going forward.