## Sheet1
Oklahoma Development Finance Authority
Preliminary Schedule of Events
Utility Ratepayer Backed Bonds (Oklahoma Gas & Electric)
Date
1921-11-01 | "Kick Off" Conference Call | Working Group
| Selection of Rating Agencies | ODFA
1921-11-04 | Circulation of 1st Draft of Indenture | PFLG
| Circulation of 1st Draft of Servicing and Sale Agreements | Norton Rose
1921-11-10 | Engagement of Rating Agencies | Treasurer's Office/Hilltop/RBC/ODFA
Stand-Up 17(g)-5 Website
| Circulation of 1st Draft of Preliminary Official Statement | Nixon
| Circulation of 1st Draft of Bond Purchase Agreement | Underwriter's Counsel
1921-11-11 | Veteran's Day Holiday
1921-11-12 | Administrative Law Judge Report Filed
1921-11-16 | Comments due on 1st Draft of Documents | Working Group
Working Group Conference Call
1921-11-17 | Submit Documents/Data/Cash Flows to Rating Agencies | Hilltop and RBC
1921-11-22 | Submit Application to Council of Bond Oversight | Hilltop
| Circulation of 2nd Draft of Indenture | PFLG
| Circulation of 2nd Draft of Servicing and Sale Agreements | Norton Rose
1921-11-24 | Circulation of 2nd Draft of Preliminary Official Statement | Nixon
| Circulation of 2nd Draft of Bond Purchase Agreement | Underwriter's Counsel
1921-11-25 | Thanksgiving Day Holiday
1921-11-30 | Hearing - Exceptions to Administrative Law Judge Report | OG&E and Hilltop
1921-12-01 | Comments due on 2nd Draft of Documents | Working Group
Working Group Conference Call
Week of December 6th | Conference Calls with Rating Agencies - Operations/Due Diligence Meeting | Hilltop/RBC/OG&E/Norton Rose
1921-12-08 | Circulation of 3rd Draft of Indenture | PFLG
| Circulation of 3rd Draft of Servicing and Sale Agreements | Norton Rose
| Circulation of 3rd Draft of Preliminary Official Statement | Nixon
| Circulation of 3rd Draft of Bond Purchase Agreement | Underwriter's Counsel
| Distribution of Board Packets to ODFA Board Members | ODFA
1921-12-15 | ODFA Board Meeting - Consideration of Financing Documents | OG&E/Hilltop/Norton Rose/RBC/ODFA
| Estimated - Financing Order Issued | OG&E/Hilltop/Norton Rose
1921-12-16 | Council of Bond Oversight Meeting - Consideration of Financing | OG&E/Hilltop/Norton Rose/RBC/ODFA
1921-12-17 | Comments due on 3rd Draft of Documents | Working Group
Working Group Conference Call
1921-12-20 | File for Supreme Court Validation | PFLG
1921-12-22 | Receipt of Supreme Court Hearing Date | PFLG
| Circulation of 4th Draft of Indenture | PFLG
| Circulation of 4th Draft of Servicing and Sale Agreements | Norton Rose
| Circulation of 4th Draft of Preliminary Official Statement | Nixon
| Circulation of 4th Draft of Bond Purchase Agreement | Underwriter's Counsel
1921-12-25 | Christmas Day Holiday
1922-01-01 | New Year's Day Holiday
Week of January 10th | Supreme Court Hearing Before Referee - Estimated Date | PFLG/Norton Rose/Hilltop
1922-01-14 | Estimated - Financing Order No Longer Subject to Appeal
1921-01-17 | Martin Luther King Jr. Day Holiday
1922-02-14 | Verbal Receipt of Preliminary Credit Ratings | Hilltop and RBC
Week of February 14th | Receipt of Supreme Court Validation Opinion - Estimated Date | PFLG/Norton Rose/Hilltop
1922-02-17 | Announcement of Transaction To Market | RBC
| Submit Preliminary Transcript to Attorney General | PFLG
1922-02-18 | Underwriter Due Diligence Call - Initial | Working Group
1922-02-21 | Presidents' Day Holiday
1922-02-22 | Post Preliminary Official Statement | Nixon
| Release of Rating Agency Pre-Sale Reports | Hilltop/RBC
February 28-March 2 | ABS Las Vegas Conference
1922-03-07 | Underwriter Due Diligence Call - Bring Down | Working Group
1922-03-09 | Pricing of Utility Ratepayer Backed Bonds (OG&E) | ODFA/Treasurer's Office/RBC/Hilltop/OG&E
1922-03-10 | Pricing of Utility Ratepayer Backed Bonds (OG&E) | ODFA/Treasurer's Office/RBC/Hilltop/OG&E
| File Pricing Information with Attorney General | PFLG
1922-03-14 | Post Official Statement | Nixon
1922-03-16 | Preferred Pre-Closing Date - Offices of Bond Counsel | Working Group
1922-03-17 | Preferred Closing Date - Offices of Bond Counsel | Working Group
1922-03-16 | Full AG Validation Period Pre-Closing Date - Offices of Bond Counsel | Working Group
1922-03-17 | Full AG Validation Period Closing Date - Offices of Bond Counsel | Working Group
2021-10-26