## Sheet1
[6 empty] | Preconstruction | [16 empty] | Construction
Preincurred
Task Name | Cost | 3rd Quarter 2015 | 4th Quarter 2015 | 1st Quarter 2016 | 2nd Quarter 2016 | 3rd Quarter 2016 | 4th Quarter 2016 | 1st Quarter 2017 | 2nd Quarter 2017 | 3rd Quarter 2017 | 4th Quarter 2017 | 1st Quarter 2018 | 2nd Quarter 2018 | 3rd Quarter 2018 | 4th Quarter 2018 | 2023 | 2024 | 2025 | 2026
Contract Design Firms | 0 | [18 empty] | 0
Finalize Project Scope | 0 | [18 empty] | 0
Preliminary Alignment | 425000 | 30357.1429 | 91071.4286 | 91071.4286 | 91071.4286 | 91071.4286 | 30357.1429 | [12 empty] | 425000
NEPA | 343000 | 16333 | 49000 | 49000 | 49000 | 49000 | 49000 | 49000 | 32667 | [10 empty] | 343000
Execute Agreements with Midwest City, Oklahoma City and Tinker Air Force Base | 0 | [18 empty] | 0
Finalize Functional Plans | 2003852 | [5 empty] | 801540.8 | 1202311.2 | [11 empty] | 2003852
Right Of Way Acquisition | 50000 | [9 empty] | 10000 | 30000 | 10000 | [6 empty] | 50000
Relocate Utilities | 50000 | [10 empty] | 10000 | 30000 | 10000 | [5 empty] | 50000
STIP/TIP Approval | 0 | [18 empty] | 0
Finalize Design Plans | 2491570 | [6 empty] | 311446.25 | 311446.25 | 311446.25 | 311446.25 | 311446.25 | 311446.25 | 311446.25 | 311446.25 |  |  |  |  | 2491570
Submit PS&E | 0 | [18 empty] | 0
Contracting | 0 | [18 empty] | 0
Reconstruct Douglas Interchange | 46000000 | [14 empty] | 11500000 | 11500000 | 11500000 | 11500000 | 46000000
Raise Westminster Road | 537000 | [14 empty] | 537000 |  |  |  | 537000
Construct center of new I-40 bridges over Anderson Road and I-240 | 2610000 | [14 empty] | 2610000 |  |  |  | 2610000
Build Inside Shoulder Eastbound for construction traffic | 6825000 | [14 empty] | 3412500 | 3412500 |  |  | 6825000
Construct WB lanes on bridges over Anderson Road and I-240 | 2610000 | [14 empty] | 1305000 | 1305000 |  |  | 2610000
Reconstruct Westbound I-40 | 20500000 | [15 empty] | 10250000 | 10250000 |  | 20500000
Construct EB lanes on bridges over Anderson Road and I-240 | 2610000 | [16 empty] | 2610000 |  | 2610000
Reconstruct Eastbound Lanes | 20500000 | [16 empty] | 10250000 | 10250000 | 20500000
Contingency | 4915435.2 | [14 empty] | 1228858.8 | 1228858.8 | 1228858.8 | 1228858.8 | 4915435.2
| 107107435.2 | [19 empty] | 112470857.2 | 107107435.2
|  | 46690.1429 | 140071.4286 | 140071.4286 | 140071.4286 | 140071.4286 | 880897.9429 | 1562757.45 | 344113.25 | 311446.25 | 321446.25 | 351446.25 | 351446.25 | 321446.25 | 311446.25 | 20593358.8 | 27696358.8 | 35838858.8 | 22978858.8 | 112470857.2 | Total Project Cost | Future Eligible Cost
Bridges at Anderson | 7830000
I-40 Widening | 47825000