## Rev. 2-8-2023
SP&R-2 ACTIVITIES TIMELINE (Critical Path and concurrent) (2/15/2023)
Milestone A | Establish Research Needs | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP
1 | Oklahoma Transportation Research Day (OTRD) | NOV: 10th; DEC: OTRD Planning meetings
2 | External/Internal Research Topics Solicitation (Problem Statements, Innovations Discovered, Research Ideas, Res. Continuance Requests) | NOV: 30th
3 | Categorization and Combination of Research Topics Received | DEC: 20th
4 | Distribution, Review and Ratings of Topic Statements by Subject Matter Experts (SME) | JAN: 31st
5 | Discuss SME Rated Research Topics, Submit Recommended Shortlist w/Deputy Chief Innovation Officer. Receive Direction and Revise. | FEB: 15th
6 | Literature and Database Searches (TRIS, RIP, Pooled Fund Studies,...) | FEB: 28th
7 | ODOT Division / District Prioritized Rankings Based on Potential Implementation / Benefits | MAR: 15th
8 | Estimate # of Projects Ending + # of Possible New Projects for Upcoming FFY | MAR: 20th
9 | Request SPR Program Manager for Estimated Funds available for SPR Part 2 Next FFY | MAR: 15th
10 | Prepare Prioritized List of Projects to be Funded (#1 General, #2 Continuing SPR, #3 Continuing TPF, #4 New SPR and TPF) | MAR: 20th
11 | Request/ Receive Deputy Chief Innovation Officer Approval of Continuing and New Research Recommended for Funding | MAR: 25th
12 | Prepare and Post Approved RFPs; Notify Contractors (Links/ Submission Forms & Guidelines) | MAR: 31st
13 | Assignment of ODOT Division Sponsor, Subject Matter Expert, RPM Project Panel | MAR: 31st
Milestone B | Selection and Approval of Proposals | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP
1 | Proposals Submitted w/Letter of Support from Division or District | 31st APR: 30th
2 | Distribution of Proposals to ODOT Subject Matter Experts | 31st MAY: 10th
3 | ODOT Subject Matter Experts' Review and Selection of Proposals | 31st MAY: 31st
4 | Obtain Commitment of Division Resources (Sponsorship Form) | 31st JUN: 10th
5 | PI Proposal Revisions (if any) | 31st JUN: 30th
6 | Approval from Subject Matter Expert(s) | 31st JUL: 10th
7 | Deputy Chief Innovation Officer Approval to Fund Sponsored Projects | 31st JUL: 20th
Milestone C | Federal Highway Administration Approval | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP
1 | Federal SP&R Part 2 Work Plan Preparation | 20th JUL: 20th
2 | Submission of SP&R Work Plan for FHWA Concurrence | 20th JUL: 31st
3 | Federal SP&R Work Plan Approval | 20th AUG: 30th
4 | Annual Performance & Expenditures Report | JAN: 10th
Milestone D | Execution of Contracts | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP
1 | Prepare Annual, Continuing and New Contracts w/Proposal attached; No Cost Extensions (NCE) | 10th JUL: 30th
2 | Transmittal to Contractor for Partial Contract Execution | 10th SEP: 15th
3 | Route for ODOT Full Contract Execution | 10th SEP: 20th
4 | Transmittal of Approved Contract Package to Contractor | 10th SEP: 30th
Milestone E | Project Administration | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP
1 | Research In Progress (RIP) Entries & Removals | OCT: 31st
2 | Project Initiation Meeting - w/Project Panel Members, PI and Assigned RPM | NOV: 10th
3 | Invoices w/Progress Reports Processing (Compliance / % complete) |  | 15th | 15th | 15th | 15th | 15th | 15th | 15th | 15th | 15th | 15th | 15th
4 | Annual Project Status / Draft Final Reports Submittal for previous FFY | OCT: 31st
5 | Engineering, Document Formatting & ADA Review of Annual, Draft Final or Final Reports | NOV: 30th
6 | Project Panel Member Review and Comments for Report Revisions | NOV: 30th
7 | Distribution of Final Report w/Revisions | DEC: 20th