## Sheet1
Project Schedule - J/P 26360(04) Bridgeport Bridge
1 | WBS | Task Name | Duration | Free Slack | Start | Finish
2 | 1 | Initiation Phase | 145 days | 0 days | Mon 6/3/19 | Fri 12/20/19
3 | 1.1 | Finalize Recon Report | 0 days | 0 days | Mon 6/3/19 | Mon 6/3/19
4 | 1.2 | Conduct Project Initiation Drive Out | 0 days | 0 days | Mon 6/3/19 | Mon 6/3/19 | complete
5 | 1.3 | Finalize Project Initiation Report | 0 days | 0 days | Mon 6/3/19 | Mon 6/3/19 | in progress
6 | 2 | Contracting Phase | 0 days | 95 days | Mon 6/3/19 | Mon 6/3/19
7 | 2.1 | Post Letters of Interest | 0 days | 0 days | Mon 6/3/19 | Mon 6/3/19
8 | 2.2 | Obtain Selection Approval | 0 days | 0 days | Mon 6/3/19 | Mon 6/3/19
9 | 2.3 | Issue Notice to Proceed | 0 days | 0 days | Mon 6/3/19 | Mon 6/3/19
10 | 3 | Preliminary Project Development Phase | 421 days | 95 days | Mon 6/3/19 | Mon 1/11/21
11 | 3.1 | Archive Survey | 0 days | 0 days | Mon 6/3/19 | Mon 6/3/19
12 | 3.2 | Finalize Hydraulic Report | 66 days | 0 days | Mon 6/3/19 | Mon 9/2/19
13 | 3.3 | Perform Preliminary Plan Field Review Meeting | 81 days | 0 days | Tue 9/3/19 | Tue 12/24/19
14 | 3.4 | Conduct Right-of-Way & Utility Meeting | 124 days | 0 days | Wed 12/25/19 | Mon 6/15/20
15 | 3.5 | Right-of-Way Plan Submission | 46 days | 65 days | Tue 6/16/20 | Tue 8/18/20
16 | 3.6 | Environmental Studies Complete | 377 days | 0 days | Mon 6/3/19 | Tue 11/10/20
17 | 3.7 | Public Involvement Complete | 5 days | 0 days | Wed 11/11/20 | Tue 11/17/20
18 | 3.8 | Finalize Environmental Document | 35 days | 0 days | Wed 11/18/20 | Tue 1/5/21
19 | 3.9 | Authorize Right-of-Way and Utility Funding | 4 days | 0 days | Wed 1/6/21 | Mon 1/11/21
20 | 4 | Final Project Develoment Phase | 102 days | 95 days | Mon 1/11/21 | Wed 6/2/21
21 | 4.1 | Perform Pedological Survey | 0 days | 0 days | Mon 1/11/21 | Mon 1/11/21
22 | 4.2 | Perform Bridge Soundings | 0 days | 0 days | Mon 1/11/21 | Mon 1/11/21
23 | 4.3 | Prepare Roadway Final Plans | 0 days | 45 days | Mon 1/11/21 | Mon 1/11/21
24 | 4.4 | Prepare Bridge Final Plans | 45 days | 0 days | Tue 1/12/21 | Mon 3/15/21
25 | 4.5 | Prepare Traffic Final Plans | 0 days | 45 days | Mon 1/11/21 | Mon 1/11/21
26 | 4.6 | Conduct Final Plan Field Review Meeting | 20 days | 0 days | Tue 3/16/21 | Mon 4/12/21
27 | 4.7 | Perform Right-of-Way Mapping | 0 days | 0 days | Mon 1/11/21 | Mon 1/11/21
28 | 4.8 | Perform Appraisal | 0 days | 0 days | Mon 1/11/21 | Mon 1/11/21
29 | 4.9 | Perform Acquisition | 0 days | 0 days | Mon 1/11/21 | Mon 1/11/21
30 | 4.1 | Perform Condemnation | 0 days | 0 days | Mon 1/11/21 | Mon 1/11/21
31 | 4.11 | Perform Relocation | 65 days | 0 days | Tue 1/12/21 | Mon 4/12/21
32 | 4.12 | Obtain Right-of-Way Legal Entry | 0 days | 0 days | Mon 4/12/21 | Mon 4/12/21
33 | 4.13 | Utility Out | 30 days | 0 days | Tue 4/13/21 | Mon 5/24/21
34 | 4.14 | Right-of-Way Certification Complete | 1 day | 0 days | Tue 5/25/21 | Tue 5/25/21
35 | 4.15 | Prepare Roadway Bridge Traffic Final Submittal Plans | 0 days | 31 days | Mon 4/12/21 | Mon 4/12/21
36 | 4.16 | Obtain 404 Corps Permit | 60 days | 36 days | Tue 1/12/21 | Mon 4/5/21
37 | 4.17 | Perform Railroad Process | 0 days | 96 days | Mon 1/11/21 | Mon 1/11/21
38 | 4.18 | Plans Complete | 5 days | 0 days | Wed 5/26/21 | Tue 6/1/21
39 | 4.19 | Ready to Let | 0 days | 0 days | Tue 6/1/21 | Tue 6/1/21
40 | 4.2 | Conduct Re-Evaluation | 1 day | 0 days | Wed 6/2/21 | Wed 6/2/21
41 | 4.21 | Submit PS&E to Office Engineer | 1 day | 98 days | Mon 5/31/21 | Mon 5/31/21
42 | 5 | Letting Phase | 76 days | 0 days | Thu 7/1/21 | Thu 10/14/21
43 | 5.1 | Receive Authorization From FHWA | 49 days | 0 days | Thu 7/1/21 | Tue 9/7/21
44 | 5.2 | Conduct Bid Opening | 15 days | 0 days | Wed 9/8/21 | Tue 9/28/21
45 | 5.3 | Conduct Pre Award Meeting | 11 days | 0 days | Wed 9/29/21 | Wed 10/13/21
46 | 5.4 | Receive Commission Approval to Award | 1 day | 0 days | Thu 10/14/21 | Thu 10/14/21
47 | 6 | Construction | 570 days | 90 days | Wed 1/12/2022 | Thu 7/20/2023