## Cost Estimate
Dallas Junction
PRELIMINARY COST ESTIMATE (Q4 2022 Dollars) 2-8-2023
Major Items
Roadway
Payitem |  |  | Quantity |  | Price per Unit | Total
202(D) | 0184 | Unclassified Borrow | 13690 | CY | 8.5 | 116365
303(A) | 2100 | Aggregate Base Type A | 30380 | CY | 67 | 2035460
307(K) | 4300 | Stabilized Subgrade | 144410 | SY | 7 | 1010870
317 | 4270 | Cement Treated Base | 128960 | SY | 18 | 2321280
325 | 5271 | Separator Fabric | 144410 | SY | 2 | 288820
408 | 5774 | Prime Coat | 80080 | GAL | 4 | 320320
414(B) | 5725 | Dowel Jointed P.C.C. Pvt. (Placement) | 121000 | SY | 29 | 3509000
414(G) | 5275 | P.C. Concrete for Pavement | 40340 | CY | 175 | 7059500
Roadway Total: | [5 empty] | 16661615
27524549.5164
Earthwork | [6 empty] | 3979056.7401
|  | Preliminary Earthwork Estimate (50%) |  |  |  | 8330807.5
Earthwork Totals: | [5 empty] | 8330807.5
Bridge
|  | I-35 SB over Oklahoma River |  |  |  | 47411925
|  | I-35 NB over Oklahoma River |  |  |  | 33894245
|  | I-35 Ramp over Oklahoma River |  |  |  | 20704695
|  | Pedestrian Bridge over Oklahoma River |  |  |  | 20020720
|  | I-35 over Stillwater RR Bridge Rehab |  |  |  | 2800000
Bridge Totals: | [5 empty] | 124831585
Major Items Total: | [5 empty] | 149824007.5
24992422.5
Minor Items
|  | Erosion Control |  |  |  | 460386.7303
|  | Clearing & Grubbing & Removals |  |  |  | 427501.9638
|  | Misc. Pipe Underdrain, Guardrail, Etc. |  |  |  | 328847.6645
|  | Mobilization, Field Office, Staking |  |  |  | 1183851.5921
|  | SWPPP Doc. & Management, Contr. Quality Control |  |  |  | 197308.5987
|  | Construction Traffic Control |  |  |  | 1249621.125
|  | Storm Sewer, Drainage |  |  |  | 1315390.6579
|  | Traffic Control |  |  |  | 690580.0954
|  | Signing & Marking |  |  |  | 657695.3289
Minor Items Total: | [5 empty] | 6511183.7566
Major Items + Minor Items Total: | [5 empty] | 156335191.2566
30% Contengency (Does Not Include Bridge) | [5 empty] | 9451081.877
Grand Total: | [5 empty] | 165786273.1336

## Bridge Estimate
265-360-150 (2022 Unit Price)
I-35 SB OVER OKLAHOMA RIVER
ITEM NO. | DESCRIPTION | UNIT | QUANT | UNIT COST | TOTAL COST
504 (A) | APPROACH SLAB | SY | 660 | 290 | 191400 | 740
504 (E) | 42" F-SHAPED PARAPET | LF | 1700 | 118 | 200600
506 (A) | STRUCTURAL STEEL | LB | 12500000 | 3 | 37500000
507 (A) | STAINLESS STEEL FIXED BEARING ASSEMBLY | EA | 55 | 2250 | 123750 | 65
507 (B) | STAINLESS STEEL EXPANSION BEARING ASSEMBLY | EA
509 (A) | CLASS AA CONCRETE | CY | 2350 | 700 | 1645000
509 (B) | CLASS A CONCRETE | CY | 1300 | 770 | 1001000 | 1000
511 (B) | EPOXY COATED REINFORCING STEEL | LB | 800000 | 1.9 | 1520000
516 (A) | DRILLED SHAFTS 72" DIAMETER | LF | 400 | 2000 | 800000 | 500
601 (B) | TYPE I-A PLAIN RIPRAP | TON | 1500 | 80 | 120000
| CONSTRUCTION TOTAL |  |  |  | 43101750
| 10% CONTINGENCY |  |  |  | 4310175
| BRIDGE TOTAL |  |  |  | 47411925
I-35 NB OVER OKLAHOMA RIVER
ITEM NO. | DESCRIPTION | UNIT | QUANT | UNIT COST | TOTAL COST
504 (A) | APPROACH SLAB | SY | 650 | 290 | 188500
504 (E) | 42" F-SHAPED PARAPET | LF | 1650 | 118 | 194700
506 (A) | STRUCTURAL STEEL | LB | 8750000 | 3 | 26250000
507 (A) | STAINLESS STEEL FIXED BEARING ASSEMBLY | EA | 45 | 2250 | 101250
507 (B) | STAINLESS STEEL EXPANSION BEARING ASSEMBLY | EA
509 (A) | CLASS AA CONCRETE | CY | 2000 | 700 | 1400000
509 (B) | CLASS A CONCRETE | CY | 950 | 770 | 731500
511 (B) | EPOXY COATED REINFORCING STEEL | LB | 650000 | 1.9 | 1235000
516 (A) | DRILLED SHAFTS 72" DIAMETER | LF | 300 | 2000 | 600000
601 (B) | TYPE I-A PLAIN RIPRAP | TON | 1400 | 80 | 112000
| CONSTRUCTION TOTAL |  |  |  | 30812950
| 10% CONTINGENCY |  |  |  | 3081295
| BRIDGE TOTAL |  |  |  | 33894245
I-35 RAMP OVER OKLAHOMA RIVER
ITEM NO. | DESCRIPTION | UNIT | QUANT | UNIT COST | TOTAL COST
504 (A) | APPROACH SLAB | SY | 300 | 290 | 87000
504 (E) | 42" F-SHAPED PARAPET | LF | 1650 | 118 | 194700
506 (A) | STRUCTURAL STEEL | LB | 5400000 | 3 | 16200000
507 (A) | STAINLESS STEEL FIXED BEARING ASSEMBLY | EA | 25 | 2250 | 56250
507 (B) | STAINLESS STEEL EXPANSION BEARING ASSEMBLY | EA
509 (A) | CLASS AA CONCRETE | CY | 1000 | 700 | 700000
509 (B) | CLASS A CONCRETE | CY | 550 | 770 | 423500
511 (B) | EPOXY COATED REINFORCING STEEL | LB | 350000 | 1.9 | 665000
516 (A) | DRILLED SHAFTS 72" DIAMETER | LF | 200 | 2000 | 400000
601 (B) | TYPE I-A PLAIN RIPRAP | TON | 1200 | 80 | 96000
| CONSTRUCTION TOTAL |  |  |  | 18822450
| 10% CONTINGENCY |  |  |  | 1882245
| BRIDGE TOTAL |  |  |  | 20704695

## Ped Bridge
PED BRIDGE OVER OKLAHOMA RIVER
ITEM NO. | DESCRIPTION | UNIT | QUANT | UNIT COST | TOTAL COST
504 (A) | APPROACH SLAB | SY | 150 | 290 | 43500 | 80
504 (E) | CONCRETE PARAPET | LF | 1700 | 105 | 178500
506 (A) | STRUCTURAL STEEL | LB | 2300000 | 3 | 6900000
507 (A) | STAINLESS STEEL FIXED BEARING ASSEMBLY | EA | 10 | 2250 | 22500
507 (B) | STAINLESS STEEL EXPANSION BEARING ASSEMBLY | EA
509 (A) | CLASS AA CONCRETE | CY | 520 | 700 | 364000 | 300
509 (B) | CLASS A CONCRETE | CY | 300 | 770 | 231000 | 60
511 (B) | EPOXY COATED REINFORCING STEEL | LB | 205000 | 1.9 | 389500 | 90000
516 (A) | DRILLED SHAFTS 72" DIAMETER | LF | 100 | 2000 | 200000 | 0
601 (B) | TYPE I-A PLAIN RIPRAP | TON | 600 | 80 | 48000 | 90
| CONSTRUCTION TOTAL |  |  |  | 8377000
| 10% CONTINGENCY |  |  |  | 837700
| CITY OF OKC MAPS 4 AESTHETICS ETC. |  |  |  | 4000000
| BRIDGE TOTAL |  |  |  | 13214700
510(D) | MSE RETAINING WALL (NORTH BANK) | SY | 4000 | 850 | 3400000
| MULTIMODAL TRAIL (NORTH BANK) | LF | 2000 | 122 | 244000
| MULTIMODAL RAMP (NORTH BANK) | LF | 500 | 1300 | 650000
| MULTIMODAL TRAIL (SOUTH BANK) | LF | 800 | 122 | 97600
| MULTIMODAL RAMP (SOUTH BANK) | LF | 500 | 1300 | 650000
| MULTIMODAL TRAIL (SOUTH BANK OKANA EXTENSION) | LF | 900 | 122 | 109800
504(F) | HANDRAILING | LF | 2800 | 30 | 84000
| CONSTRUCTION TOTAL |  |  |  | 5235400
| 30% CONTINGENCY |  |  |  | 1570620
| TRAIL TOTAL |  |  |  | 6806020
| BRIDGE & TRAIL TOTAL |  |  |  | 20020720

## Granular Schedule
Task | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Design
Pre-Construction | [7 empty] | Milestone | Date | Comments
Preliminary Study | [7 empty] | Design Survey Upgrade | 2024-06-01
Survey | [7 empty] | Preliminary Design (65%) | June-24 to July-25
Preliminary Design (up to 65%) | [7 empty] | Access Justification Report | Jan-24 to July-25 | Start at 30% Plans and complete by 65% Design
Access Justification Report (AJR) | [7 empty] | NEPA (DCE) | June-24 to July-25 | Start at 30% Plans and complete by 65% Design
NEPA (DCE) | [7 empty] | ROW Acquisition | July-25 to Dec25
Right of Way Acquistion (if necessary) | [7 empty] | Utility Relocation | July-25 to April-26
Utility Relocation | [7 empty] | Final Plans | July-25 to Feb-26
Final Plans | [7 empty] | Authorization and Letting | Feb-26 to April-26
Authorization & Letting
Construction | [7 empty] | Construction
I-35 Bridge & Multimodal Path | [7 empty] | Milestone | Date | Comments
[8 empty] | Letting Date | 2026
[8 empty] | End Construction Activities | 2029

## Granular Cost Est
Compiled on 7/31/2023
Cost Estimate
(Q4 2022 Dollars)
Item |  | Cost
Roadway
| Construction | 27500000
| Other Items (Traffic Control, Striping, Etc.) | 4000000
Bridge
| I-35 SB over Oklahoma River | 47400000
| I-35 NB over Oklahoma River | 33900000
| I-35 Ramp over Oklahoma River | 20700000
| Pedestrian Bridge over Oklahoma River | 13200000
| I-35 over Stillwater RR Bridge Rehab | 2800000
Trail Improvements |  | 5200000
| Total | 154700000
| 30% Contigency (Excluding Bridge Items) | 11010000
| Grand Total | 165710000