## Slide 1: Performance-Based Contracting
PIPS
Performance Information Procurement System
Notes: Welcome to the pre-education for the PIPS methodology, a unique procurement process that we have utilized since 2009. The Performance Information Procurement System, or PIPS, is a form of Performance Based Contracting that has been very successful in the State of Oklahoma.

## Slide 2: Performance-Based Contracting
In the performance-based approach, an agency says what problem needs to be solved and allows contractors to make bids detailing their proposed solutions.
According to:
.com
Notes: So what is Performance Based contracting? Nextgov defines Performance Based contracting as a process in which the client defines a need to be addressed and allows suppliers the opportunity to present a solution to the need. Performance Based contracting is also referred to as Best Value contracting. Basically, this allows the suppliers to utilize their expertise to solve the client’s need. PIPS has enhanced the Best Value process by utilizing common sense, natural laws and dominant information while releasing all attempts to manage, direct and control the vendor. The foundation of the process is based on Dr. Dean Kashiwagi’s companion text titled, “The Information Management Theory”.

## Slide 3: What does the PIPS approach offer?
Identifies Suppliers who can see the entire project through completion
Allows identification of all associated risks and provides for a comprehensive mitigation plan to address each risk
Process efficiencies provide win/win environment
Shifts contract management supplier to enable profit maximization
Suppliers with superior expertise can differentiate themselves
Relies on dominant information to minimize decision making
Notes: What does the PIPS approach offer? Identifies Suppliers who can see the entire project through completion. Allows identification of all associated risks and provides for a comprehensive mitigation plan to address each risk. Process efficiencies provide win/win environment. Shifts contract management supplier to enable profit maximization. Suppliers with superior expertise can differentiate themselves. Relies on dominant information to minimize decision making The primary objective of the PIPS process is to identify expertise, from the supplier community, that is capable of addressing the client need. Supplier expertise allows the supplier to “see the entire project through completion”. The ability for the supplier to see into the future is a result of the supplier having been there and done that so often that they can now anticipate risks, brought about by others, that could compromise delivery. The assumption is that because of their expertise, there is no internal risk for an expert supplier. The expert supplier has the vision that can now be utilized to identify risk that is outside of their control, when it could likely occur and provides the ability to put in place a mitigation plan to either eliminate the risk or minimize the impact should it occur. While it sounds cliché, the PIPS process is truly a win/win for both client and the supplier. This is accomplished by a number of efficiencies built into the process, one of which the shifting of contract management to the supplier. The supplier will convey contract performance through an agreed upon set of high level metrics that demonstrate progress. Cost associated with the supplier’s initial submittal are minimized as well. Respondents are given only 6 pages to convey their superior expertise which is accomplished by the conveying verifiable results from similar projects for which they provided excellent customer satisfaction. And finally, the blind evaluation process utilizes dominate information in place of subjective opinions to identify expertise. So what exactly is dominant information?

## Slide 4
It is simple
It is accurate
It is measurable
It stands out
It minimizes decision making
It predicts the future outcome
It is clearly understandable among all parties
It shows the supplier’s understanding what are required
What is dominant information?
Notes: What is dominant information? It is simple. It is accurate. It is measurable. It stands out. It minimizes decision making. It predicts the future outcome. It is clearly understandable among all parties. It shows the supplier’s understanding what are required. Dominant information can be described very simply with a outstretched arm holding a water bottle. Is there anyone that does not know what will happen when the bottle is released? Of course everyone knows how gravity works. No one needs to make a decision as to what will happen, it is clear to everyone what will happen in the future should the water bottle be released. This is dominant, it is simple, it stands out, it allow us to predicts the future and is clearly understandable to all parties.

## Slide 5
Roof material is high performing:
  Tensile strength is 800 PSI
  Elongation is 300 percent
  Tear strength is 400 lbs
  Xenon testing: 10,000 hrs
Roof material has been installed and is performing:
  65 customer responses
  Average roof age: 25 years
  Percent not leaking: 99%
  Customer satisfaction: 9.8
Non-Dominant
Dominant
Dominant
vs.
Non-Dominant
Notes: Dominant vs. Non-Dominant. Here are a couple of examples of “metrics” that vendors could provide. On the right, non-dominant side, is what we typically see in a solicitation response. The claim is Roof material is high performing and under that the vendor says: Tensile strength is 800 PSI, Elongation is 300 percent, Tear strength is 400 lbs, and Xenon testing: 10,000 hrs. On the left side under Dominant the claim is similar of Roof material has been installed and is performing but this time they make claims of 65 customer responses, Average roof age: 25 years, Percent not leaking: 99%, and Customer satisfaction: 9.8. To a roofing specialist, the information on the right hand side may seem to be dominant. An elongation of 300% and 800 PSI is likely meaningful to a roofing expert. If I was to review the specifications on the right, I would be hard pressed to understand if the roofing material specified is truly high performing because the information requires interpretation. This is not dominate. On the left side is the kind of simple, dominant information we are looking to find. It is easy to understand that the roofing material must be pretty high performing if 99% of customers with 25 year old roofs report that they are still watertight. Within the PIPS environment the information will need to be verified by the past customers, which happens later in the process.

## Slide 6
High
I. Price Based
II. Value Based
IV. Unstable Market
III. Negotiated-Bid
Specifications, standards and qualification based
Management & Inspection
Best Value (Performance and price measurements)
Quality control
Perceived Competition
Performance
Low
High
Owner selects vendor
Negotiates with vendor
Vendor performs
Contractor minimizes risk
Client minimizes risk
Industry Structure
Notes: Here under the heading of Industry Structure we see a grid that is broken up into four quadrants. On the lower right be have I. Priced Based, on the upper right we have II. Value Based, on the upper left we have III. Negotiated Bid, and on the lower left IV. Unstable Market. We have the label of “Performance on the left side showing as you move upwards towards quadrants II and III performance is higher. Along the bottom we have perceived competition so as we move from left to right the perceived competition is higher. The State of Oklahoma requires competition so I will only discuss the differences between quadrants I (1) and II (2). Quadrant number one depicts a traditional, price based award where standards, specifications and cost are the primary considerations. The primary distinction between quadrant 1 and 2 is who is responsible for minimizing risk. In quadrant one, the client tries to minimize risk contractually utilizing management, direction and control. Suppliers are held to predetermined standards and specifications even though they may not provide the optimum results. The Best Value, or value based quadrant number 2 shifts responsibility for risk mitigation to the supplier who is expected to satisfy the client’s objective. The supplier is free to perform by fully utilizing their expertise to deliver optimum results.

## Slide 7
Price based (transaction based)
  Wrong person talking
  Decision making on both sides
  Experts told to not think
  Buyer tells the vendor what to do and how to do it
Best Value (efficient, minimized transactions)
  Buyer says what he wants
  Vendors tell buyer what he can get
Performance Characteristics
Notes: Performance Characteristics. Price based (transaction based). Wrong person talking. Decision making on both sides. Experts told to not think. Buyer tells the vendor what to do and how to do it. Best Value (efficient, minimized transactions). Buyer says what he wants. Vendors tell buyer what he can get. Continuing the comparison we see the price based system has the wrong person, the client, telling the expert what to do and how to do it. In the priced based environment suppliers will not utilize their best people because their expertise is not utilized in this environment. The client makes decisions and provides direction and as a result, brings about the risk that they were hoping to avoid. Conversely, in the Best Value environment, the client or buyer states the objective and the supplier tells the client what they are able to deliver, given the client’s cost constraints. The supplier is free to utilize their best people, leverage their internal expertise, and deliver optimum results. Transactions associated with communications, decisions, relationships are minimized to achieve efficiencies unattainable in a price based environment.

## Slide 8
High
Low
Performance
The State
“The lowest possible quality that I want.”
Contractors
“The highest possible value that you will get.”
Minimum
High
Low
Performance
Maximum
Problem with Price-Based Systems
Notes: In this slide we can see the two images that show the same thing from two different perspectives. Along the left side of each box is the word performance with high at the top and low at the bottom. On the left we have The State’s point of view with a tall rectangular box that has a dotted line horizontally across it with the arrow point up above that dotted line, which has been marked as the minimum, towards the marking of High Performance at the top of the box. On the right we have the contractor’s point of view with the same rectangular box and horizontal doted line but this time the dotted line is marked as maximum and the arrow stems downward from the line towards low performance.
Price base awards will typically specify a minimum level of quality or service. The State believe this minimum requirement is at least the quality we will receive and fully expects quality will be greater than the minimum requirement. The supplier community sees the minimum as the maximum that they can offer. If vendors offer more than the minimum, they stand a real chance of pricing themselves out of the competition. Suppliers are compelled to utilize less seasoned personnel because they cannot afford to utilize their best people in a price based environment. In the Best Value-PIPS environment, the State seeks expertise and is willing to pay for this expertise knowing that a job done correctly the first time ultimately minimizes costs.

## Slide 9: Best Value vs. Low Bid
Performance
High
Low
Risk
High
Low
Contractor 1
Contractor 2
Contractor 3
Contractor 4
Contractor 1
Contractor 2
Contractor 3
Contractor 4
Performance
High
Low
Risk
High
Low
Notes: Here we have two illustrations under the heading of “Best Value vs. Lowest Bid.” In the two illustrations we again have two identical charts. Each has a tall rectangular box and along the left side we see performance and shows that as you go up performance is high and as you go down it is low. On the right we see Risk and it is inversely marked so that as you go up the box risk is low and as you go down it is high. Each has a horizontal doted line about 1/3 from the bottom, which represents that minimum standards. On the left We have contractor 1, contractor 2, contractor 3, and contractor 4 all equally distributed in the box. On the right the same contractors are all located right around the dotted line with contractors 1 and two right above and contractors 3 and 4 right below the line.
The resulting level of performance that any contractor can offer in a priced based environment is reduced as depicted on the right hand side. When price is the primary award consideration, the quality of the product or service offered is compromised to keep costs low. Contractor 1 in this example is forced to utilize less experienced people to keep overall costs competitive. Within the Best Value environment, expertise is sought and allowed to be utilized and as a result both risk and costs are minimized.

## Slide 10: PIPS Approach
Identifies suppliers who can see the entire project through completion
Focus on what is needed rather than how it will be accomplished
Process efficiencies provide win/win environment
Allows identification of all associated risks and provides for a comprehensive mitigation plan to address each risk
Suppliers with superior expertise can differentiate themselves
Shifts contract management supplier to enable profit maximization
Relies on dominant information to minimize decision making
Notes: PIPS Approach. Identifies suppliers who can see the entire project through completion. Focus on what is needed rather than how it will be accomplished. Process efficiencies provide win/win environment. Allows identification of all associated risks and provides for a comprehensive mitigation plan to address each risk. Suppliers with superior expertise can differentiate themselves. Shifts contract management supplier to enable profit maximization
Relies on dominant information to minimize decision making. Our objective within the Best Value - PIPS system is clearly to identify a supplier with the expertise to convey a vision, create a plan, manage themselves and any outside risks by having a mitigation strategy should risks materialize. Project management is minimized for both supplier and State because results and progress are conveyed through agreed upon metrics that are established during the Clarification Phase.
Allowing the expert to lead also minimizes the amount of decisions that are made. What we know about decisions is that they cause risk. Decisions are only made when it is unclear what will happen when making a particular choice. Experts make fewer decisions inherently because they have better vision as to the consequences of each choice.

## Slide 11
Level of expertise (LE)
  Claims and verifiable performance metrics
  No names or marketing materials
Risk Assessment (RA)
  Risks and mitigation plan
  No names or marketing materials
Value Added (VA)
  Claims and verifiable performance metrics
  No names or marketing materials
Project Submittals
  Two Pages
  Two Pages
  Two Pages
Notes: Project Submittals. Level of expertise (LE). Claims and verifiable performance metrics. No names or marketing materials
Risk Assessment (RA). Risks and mitigation plan. No names or marketing materials
Value Added (VA). Claims and verifiable performance metrics. No names or marketing materials
The six page Project Capability (PC) Submission represents the bulk of your response to the solicitation. As stated previously, the PC submission is made up of three components; Level of Expertise, Risk Assessment and Value Added. I will next walk you through a sample project to show examples of each of these submissions. The constraints are again repeated here; maximum of two pages for each component, and no names or marketing material. The Level of Expertise and Value Added components will convey high performance claims with metrics to verify each claim. The Risk Assessment will identify risks that are outside the suppliers control along with a mitigation plan to either eliminate or minimize the potential impact to the project.
All claims and risks should be prioritized with the most significant items list first. Again note submittals should be written in simple, non-technical language.
Also, please note that evaluations are done blindly which is why it is so important to have no identifying information in these sections. If you happen to put your organization name or identifying information it will be redacted. This is not limited to names but anything that identifies your organization. For example, if you say “We’re the current supplier for the State of Oklahoma” that will get redacted. We suggest more generic information that gives the same data. You could instead say “We’re the current supplier for a large midwestern state.” The idea is still conveyed without identifying the supplier.

## Slide 12: Project Capability Submittal
Claim:
Best project manager in company, does only clean room projects, best in the Midwest area.
Verifiable performance metrics:
Performance history for last 10 years
20 clean room projects completed
Average scope $50M
Customer satisfaction 9.5
Cost deviation .1 percent
Time deviation 1 percent
Notes: Project Capability Submittal. Claim: Best project manager in company, does only clean room projects, best in the Midwest area.
Verifiable performance metrics:
Performance history for last 10 years
20 clean room projects completed
Average scope $50M
Customer satisfaction 9.5
Cost deviation .1 percent
Time deviation 1 percent
To help drive all of this home and provide examples, I will review a sample project along with some sample responses to better illustrate what we are looking to receive. The sample project that I will use is a construction project. It is for the construction of a laboratory requiring a clean room environment. It is a fast track project, because that is typically what we work with, and it is on a university campus.
The LE example referenced here claims to have the best project manager in the company. This claim can be verified because the company has tracked his performance for the last 10 years. Over this time he has completed 20 projects of similar size, has a customer satisfaction rating of 9.5 with a cost and time and cost deviation of 1% or less. This claim is an example of one that would score a 10. It is a high value claim with verifiable metrics.

## Slide 13: Sample Risk Assessment Risk: Concrete Escalation
RA Plan 2
  The cost of concrete has been rising drastically. Since this project requires a substantial amount of concrete, cost is a risk. To minimize this risk, we have signed a contract with a local concrete manufacturer to prevent any increase in cost during the duration of this project.
RA Plan 1
  The owner can be assured all risks associated with
  material escalations will be eliminated because we offer
  the benefit of an experienced project team that includes
  the most detailed, prequalified and extensive list of
  subcontractors and suppliers from around the world.
MARKETING
Notes:   Here we have an example of two Risk Assessment submittals on the screen. At the top we have Sample Rick Assessment and below that we identify the risk as Concrete Escalation. The first, titled RA Plan 1 States: The owner can be assured all risks associated with material escalations will be eliminated because we offer the benefit of an experienced project team that includes the most detailed, prequalified and extensive list of subcontractors and suppliers from around the world. The word MARKETING is watermarked across that statement.
  Below that we have RA Plan 2, which states: The cost of concrete has been rising drastically. Since this project requires a substantial amount of concrete, cost is a risk. To minimize this risk, we have signed a contract with a local concrete manufacturer to prevent any increase in cost during the duration of this project.
  The first submission states the owner can be assured all risks associated with material escalations will be eliminated because we offer
  the benefit of an experienced project team that includes the most detailed, prequalified and extensive list of subcontractors and suppliers, from around the world……and we are supposed to take their word for this and deem the risk mitigated?
  The second submission states: The cost of concrete has been rising drastically. Since this project requires a substantial amount concrete, cost is a risk. To minimize this risk, we have and signed a contract with a local concrete manufacturer to prevent any increase in cost during the duration of this project.
  The risk has been eliminated! No need to trust in the relationships of a supplier….we have a contract in place.
Turns out the first submission is nothing but marketing material and it is questionable as to whether the risk has actually been eliminated.

## Slide 14
Claim:
Vendor will track all building major components for the first year including energy consumption, and give client recommendations to extend life of the building.
Verifiable performance metrics:
Last five buildings, vendor has done this
Performance metrics:
  9.5 customer satisfaction
  $40M scope
  Deviation rate 1 percent
  Rating on value of documentation 10 percent
  References and documentation available upon request
Value-Added Submittal
Notes: Value-added submittal.
Claim: Vendor will track all building major components for the first year including energy consumption, and give client recommendations to extend life of the building.
Verifiable performance metrics:
Last five buildings, vendor has done this
Performance metrics:
  9.5 customer satisfaction
  $40M scope
  Deviation rate 1 percent
  Rating on value of documentation 10 percent
  References and documentation available upon request
The Value Added submittal is another area that allows the state more flexibility than our traditional request for proposal process. A traditional RFP will contain a scope of work to be performed. The traditional approach assumes that the client knows exactly what is required for success and only what is within scope can be purchased. Anything outside of the “scope” will not be considered and if it were the client would be guilty of “scope creep”. The Best Value – PIPS process acknowledges that the client knows what they are trying to achieve but may not know how to get the optimum results. The PIPS process utilized the Value Added component to invite suppliers to share their good ideas that may be technically outside of the scope. Value Added services can be no cost services that are offered or could have an additional cost above and beyond what was submitted within the cost proposal. If the Value Added product or service has a cost to the client, it should not be included in the cost associated with the scope but identified within the Value Added, 2 page submission.
The Value Added submission allows suppliers to share ideas that while technically outside of the scope, would benefit the client by offering a return on the additional investment. In the example here, the scope was to build a building. The Value Added proposition is for the contractor to monitor the building for the first year and to make recommendations to extend the life of the building.
The client is able to identify Value Added proposals that would be of interest, should funds become available, prior to award. In this case, we could add on services to monitor the building performance without having to go out for another competitive bid.

## Slide 15: Selection Phase Filters and Clarification Phase
Filter 1
Project Capability
Filter 3
Prioritize
(Identify
Best Value)
Filter 4
Dominance
Check
Clarification Phase
Time
Quality of Vendors
Filter 2
Interview
Award
High
Low
Criteria
Cost
Interview
LE
RA
VA
Dominance Check
Minimized decision making in selection
Best Value is within cost range
BV dominant information is valid
Vendor clarifies proposal
Client concerns addressed
Detailed schedule
Risk activities
RMP
Performance metrics
WRR
Criteria
Level of Expertise (LE)
Risk Assessment (RA)
Value Added (VA)
Cost
Schedule
Notes: In this slide you can see a rectangular box that is set lengthwise from left to right. Outside of the box on the left we have the quality of vendors marked as low at the bottom and high at the top. At the far right is the word award. As we move from left to right there are six sections to the overall box. The first phase is the very beginning. The second box is marked Filter 1: Project Capability and has the criteria for that section which are Level of Expertise (LE), Risk Assessment (RA), Value Added (VA), Cost, and Schedule. The next box is Filter 2: Interview. The next box is Filter 3: Prioritize (Identify Best Value) and the criteria for that section of Cost, Interview, LE, RA, and VA. The next box is labeled as Filter 4: Dominance Check and what is included in that, which is Minimized decision making in selection, Best Value is within cost range, BV dominant information is valid, and the final box is labeled clarification phase with it’s criteria of Vendor clarifies proposal, Client concerns addressed, Detailed schedule, Risk activities, RMP, Performance metrics, and WRR. Starting at the very left we have a red line that starts in the bottom left corner and as we go through the sections it moves upwards towards higher quality and finally at the far right end is at the highest quality.
This slide is an overview of the selection and clarification phase. The primary focus of this presentation is to prepare suppliers for the selection phase, which is represented by the four (4) filters listed above. There will be additional education for the supplier that advances to the Clarification phase. Your objective is to reach the Clarification phase. To achieve this objective, the supplier focus should be on filters 1 and 2. Filter one (1) is your Project Capability Submittal and cost submission. A milestone schedule is requested but is not a scored component. The Project Capability Submittal is comprised of three, two page components for a total of six (6) pages. The three components are the Level of Expertise Plan, the Risk Assessment Plan, and the Value Added Plan. Each of these will be discussed in detail but it is important note that your Project Capability Submittal should be written in laymen’s terms so that anyone can understand your claims. Every member of the evaluation team should be able to understand your submittal without having to have an expert to interpret. The PC submittal should also be void of any information that could identify your organization. This “blind” submission assures that evaluators do not impart any bias within the scoring process. Any information that can be used to identify your organization should be eliminated. The State reserves the right to further redact your submission if we feel the information provided would compromise the “blind” evaluation process. Information presented in your PC submittal is assumed to be accurate and verifiable by the evaluation team. Misrepresented information within the PC submittal could lead to elimination from the Clarification process. Filter number three (2) is the interview of the supplier’s key representatives an is likely the most important filter. I’ll discuss more information on the interview process a little bit later.

## Slide 16: Performance Information Procurement System
2
Vendor is an expert
Vendor is an expert
Vendor is not an expert
Filter 1
PC
Filter 2
Interview
Filter 3
Prioritize
Filter 4
Dominance
Check
CLARIFICATION
Vendor clarifies proposal
Client concerns addressed
Detailed schedule
Risk activities
Risk mitigation plan
Performance metrics
Weekly risk report developed
AWARD
Risk Management Plan
Quality Control
Usage Reports
Weekly Risk Report
Quality Assurance
Notes: In this illustration we have three major sections that flow from left to right. Starting at the left we have an arrow pointing right that has the number 1 and says selection. Above the arrow is the phrase vendor is an expert. Underneath the arrow is a list of the 4 filters: Filter 1 PC, Filter 2 Interview, Filter 3 Prioritize, and Filter 4 Dominance Check. In the next section to the right is another arrow that has the number 2 and is labeled clarification. Below that is the phrase Vendor is not an expert. Below that are the requirements of the clarification phase listed as Vendor clarifies proposal, Client concerns addressed, Detailed schedule, Risk activities, Risk mitigation plan, Performance metrics, Weekly risk report developed. In the third and final section to the right is another arrow marked with the number 3 and labeled Management by Risk Minimization. Below that is the word award which signifies this is the award phase and work has begun. Below this are the key elements of the section listed as Weekly Risk Report, Risk Management Plan, Quality Control, Usage reports, and Quality Assurance.
This slide is an overview of the PIPS process. The focus of this training has been to communicate the requirements of the selection process. Your goal is to be identified as the vendor that possesses the most expertise and advance to the Clarification phase. The only tools you have to establish your organization’s expertise are highlighted within filters 1 and 2 above.
Notice above the selection phase is the statement “vendor is an expert”. The evaluation team will make the assumption that everything claimed within these first three filters is true and verifiable. If claims cannot be verified, the vendor can be eliminated and the next Best Value vendor can advance to Clarification.
This is where the heavy lifting begins for the vendor. Additional education will be provided should you be the one to advance, but suffice to say that this is were we will require a detailed plan that will meet the client’s objective, performance metrics will be identified and all risks will be identified along with a mitigation plan to address all risks. This is also where the client validates that expertise of the vendor by utilizing the verifiable performance metrics that were initially submitted.
Not until all documentation is created and agreed upon by client and all of the client’s concerns have been addressed will we proceed with an award.

## Slide 17
Considering:
  Pass/fail criteria (required forms)
  Scored and weighted criteria (level of expertise, risk assessment, value add, interview)
  Weighted criteria (price)
Select potential best value supplier
One supplier, the potential best value, will move forward into the clarification phase
Selection Criteria
Notes: Selection Criteria. Considering: Pass/fail criteria (required forms), Scored and weighted criteria (level of expertise, risk assessment, value add, interview), Weighted criteria (price), Select potential best value supplier, One supplier, the potential best value, will move forward into the clarification phase
To quickly review the selection criteria notice you will notice that there are still pass / fail criteria that will need to be met for your bid to be considered. To be a responsive vendor you must submit you bid before the submission deadline and you must provide a project cost. Beyond these two items, some minor irregularities can be allowed to be corrected at the discretion of the State Purchasing director. The State desires to be as inclusive as possible and if an corrected omission does not enhance a vendor’s competitiveness, it likely will be allowed.
Once passed the responsiveness test, your keys to advancement are determined by your cost and past performance submissions plus the evaluated components of the 6 page, Project Capability submission and the interviews.
Unless the State in entertaining a multiple award, only one vendor will advance to the Clarification Phase.

## Slide 18
The interview of key personnel is the event when the selection committee can get the most dominant information to identify a best value supplier.
The interview is different in the following ways:
The key person who will do the work is the one who will be interviewed.
The interview is searching for an "expert“.
The interview is non-technical.
The interview is searching for an individual who can lead a team.
The interview should have the following characteristics:
Be as short as possible. A 20 minutes duration is sufficient.
The number of questions should be limited to a few questions, and clarifications can be asked if the key personnel do not respond in a dominant fashion.
Interview
Notes: Interview. The interview of key personnel is the event when the selection committee can get the most dominant information to identify a best value supplier. The interview is different in the following ways: The key person who will do the work is the one who will be interviewed. The interview is searching for an "expert“. The interview is non-technical. The interview is searching for an individual who can lead a team. The interview should have the following characteristics: Be as short as possible. A 20 minutes duration is sufficient. The number of questions should be limited to a few questions, and clarifications can be asked if the key personnel do not respond in a dominant fashion.
The interview phase is typically weighted fairly heavily and is quite often the to component the determines the Best Value vendor. The individuals that are sent for the interview should be your most experienced people. They will also be the same individuals that will lead your team and work directly with the state to meet the State’s objective. Interviews will be very short, typically around 20 to 30 minutes, and the interviewees will be asked 4 or 5 high level questions such as, “give us a 5 minute, 20 thousand foot overview of how you will accomplish our objective from award to delivery”. Again, it takes considerable expertise to simply convey what may be a complex delivery so that everyone in the room can understand. The last thing we want is for the evaluation team to have to turn to a expert to interpret what was said.
We utilized this process for a hazardous waste contract a few years back. We bid the contract for hazardous waste every four or five years and historically one of two major national vendors will win the award, the other will protest the award. The last time we bid this contract we had a group of local former firefighters. It came time for the interviews and our evaluation team was a bit nervous as the scores were very close. When it came time to interview, the a member from the firefighters group responded to the questions. His presentation skills were lacking, he did not make eye contact, but he knew how to handle hazardous waste and scored a 10 on the interview. While he may not have been an expert at presentations or interviews, he was an expert a hazardous waste removal. So we broke the trend by awarding to the local firefighters and not one of the national vendors because of the expertise that was demonstrated. Of course, we did get a protest, which we denied for lack of grounds and it was appealed to the Agency Director who turned it over to an Administrative Law Judge. When it came time for the administrative review, the vendor did not even show up to present their case. It was the first time I recall the our legal staff was disappointed that they were unable to defend us.
What’s important to know on the interviews is that the interviewees need to be the people that will be working on the project. There is no reference material or presentation to be made. There simple, high-level question that will be asked. These should be the people that are identified in your solicitation response and it is not recommended that you send marketing or sales people as they generally lack the technical expertise that is being sought.

## Slide 19: Interview Objectives
Can the individual see into the future?
Does the individual know what they are looking for?
Does the individual see the project as complex or simple?
Is the person quick, concise, very perceptive and polite?
Can a project manager quickly identify what to do on a project?
Notes: Interview Objectives: Can the individual see into the future? Does the individual know what they are looking for? Does the individual see the project as complex or simple? Is the person quick, concise, very perceptive and polite?
Can a project manager quickly identify what to do on a project?
The individuals that are selected to represent your organization should have the ability to see into the future. No, we are not looking for people with clairvoyant powers but rather those who have the experience to be able to anticipate when and where project progress may be compromised. Their experience provides the background to know what to look and how to minimize the impact to the project. You projects leaders should be able to simply explain the delivery while understanding the client perspective.

## Slide 20: Rating System
Two components:
  Claims
  Verifiable performance measurements (VPM) to substantiate each claim
High performance claim with VPM
High/Low performance claim with no VPM
If a decision has to be made
Low performance claim with VPM
10
5
1
Notes: Rating system. Two components: Claims and Verifiable performance measurements (VPM) to substantiate each claim. High performance claim with VPM is a 10. High/Low performance claim with no VPM or If a decision has to be made is a five. And Low performance claim with VPM is a 1.
In addition to the blind evaluation, the scoring utilized in the Best Value – PIPS process is also more objective. Traditional evaluation members are asked to score each criteria utilizing a 1 through 10 scale. One evaluator may score a particular criteria as a 6 while a team member may score the same criteria as a 7. When asked to defend why one evaluator scored a 6 and another scored a 7, they are hard pressed to justify either score. Within the Best Value – PIPS model, evaluators are given only three options. Evaluators are looking for high performance claims coupled with verifiable measurements to support each claim. To receive a score of 10, suppliers must convey exceptional past performance along with supporting metrics that are verifiable. Most submissions will receive a score of 5. Scores of 5 are given if the claims are weak, if they lack supporting metrics or if the evaluator just does not know if the submission merits a 10. Evaluators are cautioned not to make decisions. They are instructed that if they find themselves trying to decide, the component should be scored a 5. A score of 1 is difficult to achieve. To score a 1, suppliers would have to convey low performance claims along with metrics to prove those claims. Poor performing suppliers seldom have metrics.

## Slide 21: Clarification Phase Deliverables
Scope of work (what is “in” and “out”)
Executive summary of project
Detailed project schedule
Detailed cost schedule
Weekly risk report
  Risk activities
  Performance measurements
  Risk mitigation plan
  Milestone schedule
Notes: Additional education will be provided should you advance to the Clarification phase. This slide note the deliverables required for the second phase which are Scope of work (what is “in” and “out”), Executive summary of project, Detailed project schedule, Detailed cost schedule, Weekly risk report, Risk activities, Performance measurements, Risk mitigation plan, and Milestone schedule
Note the primary distinction between a PIPS project and an traditional request, the vendor defines the scope of work and presents to the client what is in scope and what is out of scope.

## Slide 22
Performance metrics
Usage reports
Risk management plan
Managing Supplier Performance
Weekly Risk Reports
Notes: Managing Supplier Performance. Weekly risk Reports. Performance metrics. Usage reports. Risk management plan
The Weekly risk report is a document that will be submitted at the end of the Pre award phase. The QC Plan should contain several items:
  As we have just discussed, the Weekly risk report should contain a list of all the risks that the vendor does not control, with a plan to minimize the risks
  The Weekly risk report should contain a detailed project schedule of the actual project being procured. The schedule must identify all critical milestones and any other critical activities. If there are any critical dates where a decision is required from the client, it must also be included in the schedule.
  The Weekly risk report should also list all risks that were identified by all the other vendors in the risk assessment plans, any risks identified by the client, and must have a plan to minimize each risk.
  And finally, the Weekly risk report should contain a list of actions or tasks that the vendor requires from the client.

## Slide 23
Scope of Project
Assume No External Risk
How cost is controlled while maintaining supplier margins………
Risks Outside of Supplier Control
WEATHER
Revised Specifications
Non-responsive
Client
Notes: On this screen we have a large oval with a smaller circle in the middle. In the smaller, middle circle we see it labeled as scope of work and below that it says Assume no external risk. Outside of that circle, but within the oval, it is marked as Risks Outside of Supplier Control. On the left we have a rain cloud that is marked as weather. Below that is a man sleeping as his desk marked as Non-responsive client, and to the right there is a person looking at blueprints labeled revised specifications.
Typically the identified Best Value Supplier will also be the most cost effective solution. The reason this is possible is because the PIPS process asks that suppliers bid assuming that they will encounter no external risk. This is feasible because the PIPS process incorporates a mechanism for suppliers to charge for risks that can be shown to be outside of their control but have an impact to their costs.
PIPS assumes that due to their expertise, the supplier has no risk within their operation. All project risk for an expert resides outside of their control. A contractor hired to build a lab does not control the customer. If the customer changes the lab specifications after the project has begun, cost and timing could now be compromised at no fault of the contractor. If the contractor was working in the PIPS environment, he would be able to convey any impact to cost and timing within the weekly risk report. By assuming no external risk, the vendor is able to aggressively price projects while still having a mechanism to maintain original margins.
The Weekly Risk Report provides the transparency that holds both the client and contractor accountable for fulfilling the plan.

## Slide 24: Useful Tips
Include any legal exceptions, objections, or additions
Include verification sources for claims made in submission
No identifying information
Weekly risk report is for the clarification phase
Notes: Before closing out there are just a few tips I would like to covey to you. While none of the legal terms & conditions will be addressed until the clarification phase it is advised that organizations identify which Ts&Cs they take issue with as well as any additional terms in your initial submission. These will not be evaluated but in the clarification phase will greatly speed up the process when involving legal counsel. Also, in the initial submission you will make several claims in the project capability submission. Those ultimately have to be verified in the dominance check should you be selected to proceed to clarification. Because of this, it is recommended you include any verification of claims in your initial response. It will not be evaluated and will be a separate document from your evaluated submission and only used in the case you proceed to clarification. It is key that you do not include any identifying information in your project capability sheets as that information will be redacted and could make the information you were trying to convey not make sense. And finally, please do not worry about the Weekly Risk Report at this time. Only the vendor that proceeds to clarification will need to submit a Weekly Risk Report.

## Slide 25
QUESTIONS?
This publication is issued by the Office of Management and Enterprise Services as authorized by Title 62, Section 34. Copies have not been printed but are available through the agency website. This work is licensed under a Creative Attribution-NonCommercial-NoDerivs 3.0 Unported License.
Notes: That concludes our presentation. If you have any further questions about the PIPS process please feel free to contact Allen Cook, allen.cook@omes.ok.gov. If you have any solicitation specific questions or other concerns please contact the purchasing officer listed on the front page of the solicitation packet. Thank you.